## Slide 1: ENGINEERING MANAGEMENT (GE 404)
Tutorial # 1
Gantt Bar Chart
بسم الله الرحمن الرحيم
Instructor: Eng.Alothman
Notes: This is a title slide.

## Slide 2: About Instructor:
Name: Eng.Saleh Ibrahim Alothman
Department: Civil Engineering
Office: 2A40
Email: salothman1@Ksu.edu.sa
Office Hours: Display on office wall

## Slide 3: GANTT CHART
Attributed to Henry Gantt
Graphical way of showing:
  task durations,
  project schedule,
  Predecessor tasks on which the task depends before it
  Critical activities
Easy to understand

## Slide 4
Example 1:
Draw Gantt bar chart For a small Engineering project listed in table,
Act. | Depends on | Time (days)
A | None | 4
B | A | 6
C | B | 7
D | C, G | 3
E | None | 3
F | A, E | 4
G | F | 4
H | None | 1
I | H | 5
 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
B |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
C |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
D |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
E |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
F |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
G |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
H |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
I |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
# Project duration: 20 days
# critical activities: A, B,C ,D

## Slide 5
Activity | Predecessor | Duration (days)
A B C D E F | - A - B,C C E,B | 2 3 3 2 1 4
Example 2:
For the following project: Draw Gantt bar chart if the project starts on Sunday 16/9/2018. Consider that workdays are six days a week (Sat – Thu).
 | Sa | Su | Mo | Tu | We | Th | Fr | S | S | M | T | W | T | F
A |  |  |  |  |  |  |  |  |  |  |  |  |  | 
B |  |  |  |  |  |  |  |  |  |  |  |  |  | 
C |  |  |  |  |  |  |  |  |  |  |  |  |  | 
D |  |  |  |  |  |  |  |  |  |  |  |  |  | 
E |  |  |  |  |  |  |  |  |  |  |  |  |  | 
F |  |  |  |  |  |  |  |  |  |  |  |  |  | 
# Calendar days : 10
# Working days : 9 # Critical tasks; A, B, F

## Slide 6
Example3: The library at KSU has just received authorization to spend up to SR40,000 on new journal subscriptions and book purchases. Accordingly, the librarian has developed the following small project.
 | Task | Predecessors | Time (weeks)
A | Solicit Input from employee | - | 4
B | Identify obsolete material in library | - | 3
C | Clear out space for new purchases | B | 2
D | Hold sale/discard obsolete material | B | 3
E | Review input from employee given budget and space requirements | A, C | 2
F | Order/receive new material | E | 5
Draw Gantt bar chart for the library at KSU and use this representation to determine the expected number of weeks it will take before the new materials are in the library
Draw Gantt bar chart for this project based on the calendar days : (Use activity duration in days instead of weeks ) Starts on = start date 16/9/2018. Holidays= Friday and Saturday

## Slide 7
Draw Gantt bar chart for the library at KSU and use this representation to determine the expected number of weeks it will take before the new materials are in the library
 | Task | Predecessors | Time (weeks)
A | Solicit Input from employee | - | 4
B | Identify obsolete material in library | - | 3
C | Clear out space for new purchases | B | 2
D | Hold sale/discard obsolete material | B | 3
E | Review input from employee given budget and space requirements | A, C | 2
F | Order/receive new material | E | 5
TASK (Week) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
A |  |  |  |  |  |  |  |  |  |  |  | 
B |  |  |  |  |  |  |  |  |  |  |  | 
C |  |  |  |  |  |  |  |  |  |  |  | 
D |  |  |  |  |  |  |  |  |  |  |  | 
E |  |  |  |  |  |  |  |  |  |  |  | 
F |  |  |  |  |  |  |  |  |  |  |  | 
Project duration: 12 weeks
Critical activities: B, C, E, F

## Slide 8
Draw Gantt bar chart for this project based on the calendar days : (Use activity duration in days instead of weeks ) Assume; start date Sunday. Working days 5, Friday and Saturday Holidays
 | Task | Predecessors | Time (weeks)
A | Solicit Input from employee | - | 4
B | Identify obsolete material in library | - | 3
C | Clear out space for new purchases | B | 2
D | Hold sale/discard obsolete material | B | 3
E | Review input from employee given budget and space requirements | A, C | 2
F | Order/receive new material | E | 5
 | 1 |  |  |  |  |  |  | 2 |  |  |  |  |  |  | 3 |  |  |  |  |  |  | 4 |  |  |  |  |  |  | 5 |  |  |  |  |  |  | 6 |  |  |  |  |  | 
 | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
B |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
C |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
D |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
E |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
F |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 9
 | 7 |  |  |  |  |  |  | 8 |  |  |  |  |  |  | 9 |  |  |  |  |  |  | 10 |  |  |  |  |  |  | 11 |  |  |  |  |  |  | 12 |  |  |  |  |  | 
 | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
B |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
C |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
D |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
E |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
F |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Calendar days =84 days
Working days = 60 days
Cont.

## Slide 10: Thank You
Questions Please