## Slide 1: ENGINEERING MANAGEMENT (GE 404)
Tutorial # 7
Cash Flow
بسم الله الرحمن الرحيم
Instructor: Eng.Alothman
Notes: This is a title slide.

## Slide 2
Example1:
The following time scaled network shows the activities of a small engineering project. The cost of each activity is shown in the table below.
The contractor will receive advance payment of 15% of the project price.
This will be deducted from each monthly revenue. Application of payment will be submitted by the contractor to the client every month and payment will be after 4 weeks from the submission of the application.
The client will deduct 5% from each payment as retention . All retention will be paid to the contractor with the final payment .
Assume the markup is 20% of the total project cost and is uniformly distributed over the work. There is no delay in paying costs by the contractor.
Calculate the cash-in and cash-out values . What is max negative cash flow?
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
 | A |  |  | B |  |  | C |  |  | D |  | 
 |  |  |  |  |  | G |  |  | H |  |  | 
E |  |  |  |  | F |  |  |  |  |  |  | 
H | G | F | E | D | C | B | A | Activity
15000 | 7500 | 5000 | 15000 | 5000 | 10000 | 25000 | 10000 | Total cost

## Slide 3
Answer:
- Price = Cost*(1+M) ; M:markup= 20%
- Advanced payment = 0.15*111000 = 16650
- Retention = 0.05*111000 = 5550
Total | H | G | F | E | D | C | B | A | Activity
92500 | 15000 | 7500 | 5000 | 15000 | 5000 | 10000 | 25000 | 10000 | Total cost
111000 | 18000 | 9000 | 6000 | 18000 | 6000 | 12000 | 30000 | 12000 | Revenue

## Slide 4
 | Time (weeks) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
A (12000) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
B (30000) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
C (12000) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
D (6000) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
E (18000) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
F (6000) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
G (9000) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
H (18000) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Weekly Revenue | 13 | 13 | 4 | 13 | 13 | 10 | 8.5 | 8.5 | 4 | 11 | 11 | 2 |  |  |  |  | 
Monthly Revenue |  |  |  | 43 |  |  |  | 40 |  |  |  | 28 |  |  |  |  | 
Advanced payment | 16.65 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Retention |  |  |  |  |  |  |  |  |  |  |  | 5.55 |  |  |  |  | 
Adjust. Revenue |  |  |  | 34.4 |  |  |  | 32 |  |  |  | 22.4 |  |  |  |  | 
Income | 16.65 |  |  |  |  |  |  | 51.05 |  |  |  | 83.05 |  |  |  | 111 | 
Cost |  |  |  | 35.83 |  |  |  | 33.3 |  |  |  | 23.3 |  |  |  |  | 
Cumulative Cost |  |  |  | 35.83 |  |  |  | 69.17 |  |  |  | 92.5 |  |  |  | 92.5 | 
Net Cash flow | 16.65 |  |  | -19.18 |  |  |  | -52.51 -18.12 |  |  |  | -41.45 -9.45 |  |  |  | -9.45 18.5 | 
4
4
4
10
10
10
4
4
4
2
2
2
9
9
3
3
4.5
4.5
9
9

## Slide 5
Income | 16.65 |  |  |  |  |  |  | 51.05 |  |  |  | 83.05 |  |  |  | 111 | 
Cost |  |  |  | 35.83 |  |  |  | 33.3 |  |  |  | 23.3 |  |  |  |  | 
Cumulative Cost |  |  |  | 35.83 |  |  |  | 69.17 |  |  |  | 92.5 |  |  |  | 92.5 | 
Net Cash flow | 16.65 |  |  | -19.18 |  |  |  | -52.51 -18.12 |  |  |  | -41.45 -9.45 |  |  |  | -9.45 18.5 | 
Chart: Time(weeks)
| 0 | 4 | 4 | 8 | 8 | 12 | 12 | 16 | 16
Expense | 0 | 35.83 | 35.83 | 69.17 | 69.17 | 92.5 | 92.5 | 92.5 | 92.5
Net Cash flow | 16.65 | -19.18 | -19.18 | -52.51 | -18.12 | -41.45 | -9.45 | -9.45 | 18.5
Income | 16.65 | 16.65 | 51.05 | 51.05 | 83.05 | 83.05 | 111

## Slide 6
Example2:
Consider data for a small project given in Table below. Revenue is paid to the contractor every 3 months according to completed quantities of work. Assume that markup is 15% of total project cost and is uniformly distributed over the work.
Assume also that work of each activity is uniformly distributed over its duration.
  Draw on a scale the project cumulative cost and revenue curves according to ES timings.
  Draw on the diagram produced in a) above effect of receipt of 20% of total revenue as an advance payment. This payment will be deducted from each periodic revenue by the same percentage.
Activity | Predecessor(s) | Duration, Months | Monthly cost, 10,000 SR
A | - | 4 | 6
B | A | 6 | 12
C | A | 4 | 14
D | C | 5 | 10
E | B | 3 | 10
F | D, E | 2 | 10

## Slide 7
A 4
B 6
C 4
D 5
E 3
F 2
Solution
Project completion time 15 months;
(Critical Path’s Activities A–B–E-F; A-C-D-F)
TIME | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
 |  |  |  |  |  |  |  | B-12 |  |  |  | E-10 |  |  | 
 |  | A-6 |  |  |  |  |  |  |  |  |  |  |  |  | F-10
 |  |  |  |  |  | C-14 |  |  |  |  |  | D-10 |  |  | 
TIME | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Cost | 6 | 6 | 6 | 6 | 26 | 26 | 26 | 26 | 22 | 22 | 20 | 20 | 20 | 10 | 10
ACC. COST | 6 | 12 | 18 | 24 | 50 | 76 | 102 | 128 | 150 | 172 | 192 | 212 | 232 | 242 | 252
1. Activity Cost distribution
2. Payment
Total payment = 252*(1+0.15) x 10,000=289.8 x 10,000=2,898,000 SR
Advanced payment = 0.2*2,898,000=579,600 SR

## Slide 8
3. Revenue calculation every 3 months
TIME | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Cum. COST |  | 6 | 12 | 18 | 24 | 50 | 76 | 102 | 128 | 150 | 172 | 192 | 212 | 232 | 242 | 252
Cum. Adj Revenue | 57.96 |  |  | 74.52 |  |  | 126.88 |  |  | 195.96 |  |  | 253 |  |  | 289.8
Month | R= Revenue =(Cost*1.15), 10,000 SR | Adj. Revenue = 0.8R, 10,000 SR | Cumulative adj. Revenue, 10,000 SR
0 |  |  | 57.96
3 | 18(1.15)=20.7 | 16.56 | 16.56+57.96=74.52
6 | 76(1.15)=87.4 | 68.92 | 68.92+57.96=126.88
9 | 150(1.15)=172.5 | 138 | 138+57.96=195.96
12 | 212(1.15)=243.8 | 195.04 | 195.04+57.96=253
15 | 252(1.15)=289.8 | 231.84 | 231.84+57.96=289.8

## Slide 9
4- Graph presentations for payment every 3 months
Chart: Time (months)
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Com. Cost | 0 | 6 | 12 | 18 | 24 | 50 | 76 | 102 | 128 | 150 | 172 | 192 | 212 | 232 | 242 | 252
Revenue | 0 | 0 | 0 | 0 | 20.7 | 20.7 | 20.7 | 20.7 | 87.4 | 87.4 | 87.4 | 87.4 | 172.5 | 172.5 | 172.5 | 172.5 | 243.8 | 243.8 | 243.8 | 243.8 | 289.8
Adj. revenue | 57.96 | 57.96 | 57.96 | 57.96 | 74.52 | 74.52 | 74.52 | 74.52 | 126.88 | 126.88 | 126.88 | 126.88 | 195.96 | 195.96 | 195.96 | 195.96 | 253 | 253 | 253 | 253 | 289.8
Cumulative Cash Flow
Chart: Project Duration, month
| 0 | 1 | 2 | 3 | 3 | 4 | 5 | 6 | 6 | 7 | 8 | 9 | 9 | 10 | 11 | 12 | 12 | 13 | 14 | 14 | 15
Adjusted Revenue | 60.26 | 54.26 | 48.26 | 42.26 | 58.82 | 52.82 | 16.82 | -9.18 | 46.02 | 20.02 | -5.98 | -27.98 | 47.46 | 25.46 | 5.46 | -14.54 | 42.5 | 22.5 | 12.5 | 49.3 | 39.3
Revenue | 0 | -6 | -12 | -18 | 2.7 | -3.3 | -39.3 | -65.3 | 12.9 | -13.1 | -39.1 | -61.1 | 24 | 2 | -18 | -38 | 33.3 | 13.3 | 3.3 | 49.3 | 39.3
Net Cash Flow

## Slide 10: Thank You
Questions Please