## Slide 1: ENGINEERING MANAGEMENT (GE 404)
Tutorial # 8
Project Time Control
بسم الله الرحمن الرحيم
Instructor: Eng.Alothman
Notes: This is a title slide.

## Slide 2
Measure and Report Progress
Methods
Estimated number of working days req. to complete the activity.
Estimated % completion of the activity.
Quantities of work units put in place.
Equations
Working days to complete = d (1 - P/100)
Working days to complete = d (1 – (W/T))
Where
  d= total activity duration in working days
  P = estimated percentage of completion
  W= number of work units put into place.
  T= total number of work units associated with the activity.
Based on the assumption of straight-line variation between time and work accomplishment

## Slide 3
Example1:
The initial AON diagram for a small engineering project is shown below with its planned activity times in weeks.
At the end of the 5th week, the field progress report gives you the following information:
Activities “B, C, D and E” have been completed on schedule.
Activity “F” is ready to start at the beginning of the week 6.
Remaining duration of activity “H” is 4 weeks.
Remaining duration of activity “I” is 3 weeks.
Activity “G” will not start until end of week 7.
Volume of work in activity “L” has been increased by 33% approximately.
Activity “J” has been omitted
It is decided to shorten activity “K” by 2 weeks.
Construct the updated schedule indicating the critical path and showing new activities times.

## Slide 4
2 | 2 | 4
E |  | 
14 |  | 16
2 | 6 | 8
F |  | 
5 |  | 11
5 | 6 | 11
G |  | 
5 |  | 11
3 | 6 | 9
H |  | 
9 |  | 15
3 | 4 | 7
I |  | 
12 |  | 16
0 | 0 | 0
START |  | 
0 |  | 0
0 | 2 | 2
B |  | 
3 |  | 5
0 | 5 | 5
C |  | 
0 |  | 5
0 | 3 | 3
D |  | 
6 |  | 9
18 | 2 | 20
N |  | 
18 |  | 20
9 | 2 | 11
M |  | 
16 |  | 18
9 | 3 | 12
L |  | 
15 |  | 18
11 | 7 | 18
K |  | 
11 |  | 18
8 | 2 | 10
J |  | 
16 |  | 18

## Slide 5
 | 0 | 
E |  | 
2 | 6 | 8
F |  | 
5 |  | 11
5 | 6 | 11
G |  | 
5 |  | 11
3 | 6 | 9
H |  | 
9 |  | 15
3 | 4 | 7
I |  | 
12 |  | 16
0 | 0 | 0
START |  | 
0 |  | 0
 | 0 | 
B |  | 
 | 0 | 
C |  | 
 | 0 | 
D |  | 
18 | 2 | 20
N |  | 
18 |  | 20
9 | 2 | 11
M |  | 
16 |  | 18
9 | 3 | 12
L |  | 
15 |  | 18
11 | 7 | 18
K |  | 
11 |  | 18
8 | 2 | 10
J |  | 
16 |  | 18
At the end of the 5th week, the field progress report gives you the following information:
Activities “B, C, D and E” have been completed on schedule.

## Slide 6
 | 0 | 
E |  | 
5 | 6 | 11
F |  | 
5 |  | 11
5 | 6 | 11
G |  | 
5 |  | 11
3 | 6 | 9
H |  | 
9 |  | 15
3 | 4 | 7
I |  | 
12 |  | 16
0 | 0 | 0
START |  | 
0 |  | 0
 | 0 | 
B |  | 
 | 0 | 
C |  | 
 | 0 | 
D |  | 
18 | 2 | 20
N |  | 
18 |  | 20
9 | 2 | 11
M |  | 
16 |  | 18
9 | 3 | 12
L |  | 
15 |  | 18
11 | 7 | 18
K |  | 
11 |  | 18
11 | 2 | 13
J |  | 
16 |  | 18
LIVE
At the end of the 5th week, the field progress report gives you the following information:
Activity “F” is ready to start at the beginning of the week 6.

## Slide 7
 | 0 | 
E |  | 
5 | 6 | 11
F |  | 
5 |  | 11
5 | 6 | 11
G |  | 
5 |  | 11
5 | 4 | 9
H |  | 
9 |  | 15
3 | 4 | 7
I |  | 
12 |  | 16
0 | 0 | 0
START |  | 
0 |  | 0
 | 0 | 
B |  | 
 | 0 | 
C |  | 
 | 0 | 
D |  | 
18 | 2 | 20
N |  | 
18 |  | 20
9 | 2 | 11
M |  | 
16 |  | 18
9 | 3 | 12
L |  | 
15 |  | 18
11 | 7 | 18
K |  | 
11 |  | 18
11 | 2 | 13
J |  | 
16 |  | 18
LIVE
LIVE
At the end of the 5th week, the field progress report gives you the following information:
Remaining duration of activity “H” is 4 weeks.

## Slide 8
 | 0 | 
E |  | 
5 | 6 | 11
F |  | 
5 |  | 11
5 | 6 | 11
G |  | 
5 |  | 11
5 | 4 | 9
H |  | 
9 |  | 15
5 | 3 | 8
I |  | 
12 |  | 16
0 | 0 | 0
START |  | 
0 |  | 0
 | 0 | 
B |  | 
 | 0 | 
C |  | 
 | 0 | 
D |  | 
18 | 2 | 20
N |  | 
18 |  | 20
9 | 2 | 11
M |  | 
16 |  | 18
9 | 3 | 12
L |  | 
15 |  | 18
11 | 7 | 18
K |  | 
11 |  | 18
11 | 2 | 13
J |  | 
16 |  | 18
LIVE
LIVE
LIVE
At the end of the 5th week, the field progress report gives you the following information:
Remaining duration of activity “I” is 3 weeks.

## Slide 9
 | 0 | 
E |  | 
5 | 6 | 11
F |  | 
7 |  | 13
7 | 6 | 13
G |  | 
7 |  | 13
5 | 4 | 9
H |  | 
13 |  | 17
5 | 3 | 8
I |  | 
15 |  | 18
0 | 0 | 0
START |  | 
0 |  | 0
 | 0 | 
B |  | 
 | 0 | 
C |  | 
 | 0 | 
D |  | 
20 | 2 | 22
N |  | 
20 |  | 22
9 | 2 | 11
M |  | 
18 |  | 20
9 | 3 | 12
L |  | 
17 |  | 20
13 | 7 | 20
K |  | 
13 |  | 20
11 | 2 | 13
J |  | 
18 |  | 20
LIVE
LIVE
LIVE
At the end of the 5th week, the field progress report gives you the following information:
Activity “G” will not start until end of week 7.
Remark:
As G start late, this affect times all activities successors and reflect on times

## Slide 10
 | 0 | 
E |  | 
5 | 6 | 11
F |  | 
7 |  | 13
7 | 6 | 13
G |  | 
7 |  | 13
5 | 4 | 9
H |  | 
13 |  | 17
5 | 3 | 8
I |  | 
15 |  | 18
0 | 0 | 0
START |  | 
0 |  | 0
 | 0 | 
B |  | 
 | 0 | 
C |  | 
 | 0 | 
D |  | 
20 | 2 | 22
N |  | 
20 |  | 22
9 | 2 | 11
M |  | 
18 |  | 20
9 | 4 | 13
L |  | 
17 |  | 20
13 | 7 | 20
K |  | 
13 |  | 20
11 | 2 | 13
J |  | 
18 |  | 20
LIVE
LIVE
LIVE
At the end of the 5th week, the field progress report gives you the following information:
Volume of work in activity “L” has been increased by 33% approximately.

## Slide 11
 | 0 | 
E |  | 
5 | 6 | 11
F |  | 
7 |  | 13
7 | 6 | 13
G |  | 
7 |  | 13
5 | 4 | 9
H |  | 
13 |  | 17
5 | 3 | 8
I |  | 
15 |  | 18
0 | 0 | 0
START |  | 
0 |  | 0
 | 0 | 
B |  | 
 | 0 | 
C |  | 
 | 0 | 
D |  | 
20 | 2 | 22
N |  | 
20 |  | 22
9 | 2 | 11
M |  | 
18 |  | 20
9 | 4 | 13
L |  | 
17 |  | 20
13 | 7 | 20
K |  | 
13 |  | 20
 | 0 | 
J |  | 
LIVE
LIVE
LIVE
At the end of the 5th week, the field progress report gives you the following information:
Activity “J” has been omitted

## Slide 12
 | 0 | 
E |  | 
5 | 6 | 11
F |  | 
7 |  | 13
7 | 6 | 13
G |  | 
7 |  | 13
5 | 4 | 9
H |  | 
11 |  | 15
5 | 3 | 8
I |  | 
13 |  | 16
0 | 0 | 0
START |  | 
0 |  | 0
 | 0 | 
B |  | 
 | 0 | 
C |  | 
 | 0 | 
D |  | 
18 | 2 | 20
N |  | 
18 |  | 20
9 | 2 | 11
M |  | 
16 |  | 18
9 | 4 | 13
L |  | 
15 |  | 18
13 | 5 | 18
K |  | 
13 |  | 18
J |  | 
LIVE
LIVE
LIVE
At the end of the 5th week, the field progress report gives you the following information:
It is decided to shorten activity “K” by 2 weeks.
Remark:
As k duration is reduced, this affect times all activities successors and reflect on times

## Slide 13
E |  | 
5 | 6 | 11
F |  | 
7 |  | 13
7 | 6 | 13
G |  | 
7 |  | 13
5 | 4 | 9
H |  | 
11 |  | 15
5 | 3 | 8
I |  | 
13 |  | 16
0 | 0 | 0
START |  | 
0 |  | 0
B |  | 
C |  | 
D |  | 
18 | 2 | 20
N |  | 
18 |  | 20
9 | 2 | 11
M |  | 
16 |  | 18
9 | 4 | 13
L |  | 
15 |  | 18
13 | 5 | 18
K |  | 
13 |  | 18
J |  | 
Modified AON at the end of the 5th week, after adjusting changes
Critical Path:
G,K,N

## Slide 14: Thank You
Questions Please