## Slide 1: ENGINEERING MANAGEMENT (GE 404)
Tutorial # 9
Project Cost Control
بسم الله الرحمن الرحيم
Instructor: Eng.Alothman
Notes: This is a title slide.

## Slide 2
BCWP
ACWP
= 0
> 0
< 0
Under budget
Work performed cost > Actual cost
Within budget
Work performed cost = Actual cost
Over budget
Work performed cost < Actual cost
Cost Performance
BCWP
ACWP
= 0
> 0
< 0
Under run
Performed cost > Earned
on run
Performed cost = Earned
Over run
Performed cost < Earned
Cost Performance
The “Cost Overrun” curve is a plot of the calculated percent over- or Underrun at any given time.
BCWP
ACWP
= 1
> 1
< 1
Under budget
Work performed cost > Actual cost
Within budget
Work performed cost = Actual cost
Over budget
Work performed cost < Actual cost
Cost Performance
Performance Equations
Symbol | Definition | التعريف
(BCWS) [PV]” | Budgeted Cost of Work Scheduled “planned value of work to be accomplished | تكلفة موازنة للأعمال المجدولة وفقا للخطة
(BCWP) [EV] | Budgeted Cost of Work Performed “earned value of work accomplished | تكلفة موازنة لما تم من أعمال
(ACWP) [AC] | Actual Cost of Work Performed | التكلفة الفعلية لما تم من أعمال وتم دفعها
Cost Performance Index | CPI = BCWP/ACWP
Cost Variance | CV = BCWP-ACWP
% Cost Overrun/ Underrun | )
% Cost Overrun/ Underrun | 

## Slide 3
Performance Equations
Symbol | Definition | التعريف
(BCWS) [PV]” | Budgeted Cost of Work Scheduled “planned value of work to be accomplished | تكلفة موازنة للأعمال المجدولة وفقا للخطة
(BCWP) [EV] | Budgeted Cost of Work Performed “earned value of work accomplished | تكلفة موازنة لما تم من أعمال
(ACWP) [AC] | Actual Cost of Work Performed | التكلفة الفعلية لما تم من أعمال وتم دفعها
BCWP
BCWS
= 0
> 1
< 1
Ahead schedule
Work performed > Work scheduled
On schedule
Work performed = Work scheduled
Behind scheduke
Work performed < Work scheduled
Schedule (Time) Performance
BCWP
BCWS
= 0
> 0
< 0
Ahead schedule
Work performed > Work scheduled
On schedule
Work performed = Work scheduled
Behind scheduke
Work performed < Work scheduled
Schedule (Time) Performance
Schedule/Performance Variance | SV = BCWP-BCWS
Schedule Performance Index | SPI = BCWP/BCWS

## Slide 4
Performance Equations
Symbol | Definition | التعريف
(BCWS) [PV]” | Budgeted Cost of Work Scheduled “planned value of work to be accomplished | تكلفة موازنة للأعمال المجدولة وفقا للخطة
(BCWP) [EV] | Budgeted Cost of Work Performed “earned value of work accomplished | تكلفة موازنة لما تم من أعمال
(ACWP) [AC] | Actual Cost of Work Performed | التكلفة الفعلية لما تم من أعمال وتم دفعها
Estimated Cost At Completion | * BAC, OR
Estimated Cost At Completion | 
Estimate to Completion | ETC = EAC - ACWP
Budget Cost At Completion | BAC = BCWSend
Variance from original budget | VB = EAC - BAC

## Slide 5
BCWS [PV], BCWP [EV], and ACWP[AC] – S-CURVES
BCWP [EV]
BCWS [PV]
ACWP [AC]

## Slide 6
Activity | Original Planned Start | Original Planned Finish | Percent Complete | Original Planned Cost,$ | Amount Spent,$
A | 0 | 10 | 100% | 6000 | 5000
B | 0 | 8 | 100% | 8000 | 10000
C | 8 | 16 | 75% | 8000 | 7000
D | 8 | 24 | 90% | 7000 | 5000
E | 10 | 20 | 80% | 10000 | 6000
F | 16 | 24 | 75% | 6000 | 4000
G | 20 | 28 | 25% | 8000 | 3000
H | 24 | 30 | 0% | 9000 | 0
I | 28 | 30 | 0% | 3000 | 0
Determine the budgeted cost of work scheduled
Determine the Budgeted cost of work performed.
Determine the actual cost of work performed.
Determine the cost variance and schedule variance.
Example1:
For the project whose activities by 20 days are summarized in the table below (referring to the whole project not just the individuals activities)

## Slide 7
Activity | (1) Original Planned Start | (2) Original Planned Finish | (3) Percent Complete | (4) Original Planned Cost,$ | (5) Amount Spent,$ | (6) Amount Completed,$ | (7) Amount Scheduled,$
A | 0 | 10 | 1 | 6000 | 5000 |  | 
B | 0 | 8 | 1 | 8000 | 10000 |  | 
C | 8 | 16 | 0.75 | 8000 | 7000 |  | 
D | 8 | 24 | 0.9 | 7000 | 5000 |  | 
E | 10 | 20 | 0.8 | 10000 | 6000 |  | 
F | 16 | 24 | 0.75 | 6000 | 4000 |  | 
G | 20 | 28 | 0.25 | 8000 | 3000 |  | 
H | 24 | 30 | 0 | 9000 | 0 |  | 
I | 28 | 30 | 0 | 3000 | 0 |  | 
 |  |  |  |  | ACWP = $40000 | BCWP = | BCWS =
Cost monitor at milestone Time, Tc = 20

## Slide 8
Activity | (1) Original Planned Start | (2) Original Planned Finish | (3) Percent Complete | (4) Original Planned Cost,$ | (5) Amount Spent,$ | (6) Amount Completed,$ | (7) Amount Scheduled,$
A | 0 | 10 | 1 | 6000 | 5000 | 6000 | 
B | 0 | 8 | 1 | 8000 | 10000 | 8000 | 
C | 8 | 16 | 0.75 | 8000 | 7000 | 6000 | 
D | 8 | 24 | 0.9 | 7000 | 5000 | 6300 | 
E | 10 | 20 | 0.8 | 10000 | 6000 | 8000 | 
F | 16 | 24 | 0.75 | 6000 | 4000 | 4500 | 
G | 20 | 28 | 0.25 | 8000 | 3000 | 2000 | 
H | 24 | 30 | 0 | 9000 | 0 | 0 | 
I | 28 | 30 | 0 | 3000 | 0 | 0 | 
 |  |  |  |  | ACWP = $40000 | BCWP = $40800 | BCWS =
Remark:
Amount completed = % completed (3) * planned Cost (4)
Cost monitor at milestone Time, Tc = 20

## Slide 9
Activity | (1) Original Planned Start | (2) Original Planned Finish | (3) Percent Complete | (4) Original Planned Cost,$ | (5) Amount Spent,$ | (6) Amount Completed,$ | (7) Amount Scheduled,$
A | 0 | 10 | 1 | 6000 | 5000 | 6000 | 6000
B | 0 | 8 | 1 | 8000 | 10000 | 8000 | 8000
C | 8 | 16 | 0.75 | 8000 | 7000 | 6000 | 8000
D | 8 | 24 | 0.9 | 7000 | 5000 | 6300 | 5250
E | 10 | 20 | 0.8 | 10000 | 6000 | 8000 | 10000
F | 16 | 24 | 0.75 | 6000 | 4000 | 4500 | 3000
G | 20 | 28 | 0.25 | 8000 | 3000 | 2000 | 0
H | 24 | 30 | 0 | 9000 | 0 | 0 | 0
I | 28 | 30 | 0 | 3000 | 0 | 0 | 0
 |  |  |  |  | ACWP = $40000 | BCWP = $40800 | BCWS = $40250
Remark:
Amount of scheduled = Planned cost (4) * percent produced for activity more the milestone time (time from start to milestone/ duration); for D = (20-8)/(24-8)=0.75
Cost monitor at milestone Time, Tc = 20

## Slide 10
Schedule Variance = BCWP – BCWS
= (40800- 40250) = $550
Ahead of Schedule
Variance determination
Cost Variance = BCWP – ACWP =
= (40800- 40000) = $800
Under Budget

## Slide 11
The following time-scale diagram represents a small engineering project. The budgeted cost of each activity is shown in the table below. At the end of the 10th week, the field progress report gives you the following information:
Activity “A” was completed on schedule.
Activity “B” started as planned but it is expected to take four weeks more.
Activity “C” started as planned but finished one week later.
%age of completion of activity “D” is 60%.
ACWP at the end of week 10 = SR 90400
Calculate the CV, SV, BAC, EAC, ETC
Time (week) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
A (5 weeks) |  |  |  |  | B (8 weeks) |  |  |  |  |  |  |  | E (7 weeks) |  |  |  |  |  |  | F (3 weeks) |  | 
C (5weeks) |  |  |  |  | D (6 weeks) |  |  |  |  |  |  |  | G (4 weeks) |  |  |  |  |  |  |  |  | 
Activity | A | B | C | D | E | F | G
Budgeted cost (SR) | 50000 | 12000 | 16000 | 24000 | 12000 | 21000 | 20000
Example:2

## Slide 12
Activity | Original Planned Start | Original Planned Finish | Percent Complete | Original Planned Cost
A | 0 | 5 | 100% | $50000
B | 5 | 13 | 41.66666% | $12000
C | 0 | 5 | 100% | $16000
D | 5 | 11 | 60% | $24000
E | 13 | 20 | 0% | $12000
F | 20 | 23 | 0% | $21000
G | 13 | 17 | 0% | $20000
%age of completion of activity “A” = 100%
Projected duration of activity “B” = 8 + 4 = 12 weeks
%age of completion of activity “B” = 5/12 = 41.666666%
%age of completion of activity “C” = 100%
Activity “A” was completed on schedule.
Activity “B” started as planned but it is expected to take four weeks more.
Activity “C” started as planned but finished one week later.
%age of completion of activity “D” is 60%.
ACWP at the end of week 10 = $ 90400

## Slide 13
Activity | Original Planned Start | Original Planned Finish | Percent Complete | Original Planned Cost | Amount Completed | Amount Scheduled
A | 0 | 5 | 100% | $50000 | $50000 | $50000
B | 5 | 13 | 41.666% | $12000 | $5000 | $7500
C | 0 | 5 | 100% | $16000 | $16000 | $16000
D | 5 | 11 | 60% | $24000 | 14400 | $20000
E | 13 | 20 | 0% | $12000 | $0 | $0
F | 20 | 23 | 0% | $21000 | $0 | $0
G | 13 | 17 | 0% | $20000 | $0 | $0
 |  |  |  |  | BCWP = $ 85400 | BCWS = $93500
CV = BCWP – ACWP = 85400 – 90400 = $-5000 (Over Budget)
SV = BCWP – BCWS = 85400 – 93500 = $ -8100 (Behind Schedule)
BAC = 50000 + 12000 + 16000 + 24000 + 12000 + 21000 + 20000 = SR 155000
EAC = [ACWP/BCWP]*BAC = [90400/85400]*155000 = SR 164075
ETC = EAC – ACWP = 164075 – 90400 = SR 73675

## Slide 14
The following time-scaled network shows the activities of a small engineering project.
The budgeted cost of each activity is shown in Table below.
Example:3
Table. Activity budgeted cost |  |  |  |  |  |  |  | 
Activity | A | B | C | D | E | F | G | H
Budgeted cost (SR) | 4000 | 6000 | 2000 | 8000 | 7000 | 6000 | 9000 | 4000
The budgeted cost of each activity is assumed to be uniformly distributed over its duration. At the end of the 15th day, the field progress report gives you the following information:
Activity “A” was completed on schedule.
Due to owner fault, the actual start of activity “B” was on the morning of day 12. Activity “B” is still in progress.
Activity “C” finished at the end of the 7th day.
The percentage of completion of activity "D" is 80%.
Activity “E” was completed as planned.
Activity “F” started as planned but its duration is expected to be 12 days instead of 15 days.
ACWP at the end of day 15 = SR 20400.
Calculate the CV, SV, CPI, SPI, and % overrun (underrun); BAC, EAC; comment on progress of works.

## Slide 15
BCWS = 4000 + 6000 (7/12) + 2000 + 8000 + 7000 + 6000 (8/15) = SR27,700
BCWP = 4000 + 6000 (4/12) + 2000 + 8000 (0.8) + 7000 + 6000 (8/12) = SR25,400
ACWP = SR 20,400
CV = BCWP – ACWP = SR5000  under budget
SV = BCWP – BCWS = SR -2,300  Behind the schedule
BAC = 4000 + 6000 + 2000 + 8000 + 7000 + 6000 +9000 + 4000 = SR 46,000
EAC = (ACWP/ BCWP) × BAC = SR36,944.88
ETC = EAC – ACWP = SR16,544
% overrun or underrun = (ACWP-BCWP)/BCWP = -20% underrun

## Slide 16: Thank You
Questions Please