## Slide 1: Chapter 9: Project Resource Management
Note: See the text itself for full citations.
Information Technology Project Management, ninth Edition

## Slide 2: The Importance of Human Resource Management
Many corporate executives have said, “People are our most important asset”
People determine the success and failure of organizations and projects

## Slide 3: The Global IT Workforce
Although there have been ups and downs in the IT labor market, there will always be a need for good IT workers
The number of jobs available to IT professionals is expected to increase by 12 percent by 2024. “While job seekers will offer an array of technical skills, employers are typically looking for a more balanced employee who also possesses soft skills that are not readily apparent on a resume.

## Slide 4: Implications for the Future of IT Human Resource Management
If organizations want to implement IT projects successfully, they need to understand the importance of project resource management and make effective use of people.
Proactive organizations are addressing workforce needs by
  improving benefits
  redefining work hours and incentives
  finding future workers

## Slide 5
Google, the winner of Fortune’s 100 Best Companies award multiple times in recent years, provides employees with free gourmet meals, on-site doctors, a swimming spa and corporate gym, beach volleyball, Foosball, video games, pool tables, ping-pong, roller hockey, and weekly Thank Goodness It’s Friday (TGIF) parties! Google built a large, outdoor sports complex in 2011 to help keep its employees in shape. The company also provides indoor recreation with bowling alleys and a dance studio, and offers a generous amount of leave for new parents (regardless of gender, including dads, domestic partners, adoptive parents, and surrogate parents)—12 weeks of fully paid “baby bonding” plus $500.* With an average of 130 applicants per hire, it’s almost ten times harder to get a job at Google than it is to get into Harvard.

## Slide 6: What is Project Resource Management?
The processes required for Making the most effective use of the human and physical resources (facilities, equipment, materials, supplies, etc.) involved with a project.
Human resource management includes all project stakeholders: sponsors, customers, project team members, support staff, suppliers supporting the project, and so on. Physical resources include facilities, equipment, materials, and supplies.

## Slide 7: Project Resource Management Processes
Planning resource management involves deciding how to estimate, acquire, manage, and use project resources. The main outputs are a resource management plan, team charter, and project documents updates.
Estimating activity resources involves estimating human and physical resources needed to complete project work. Outputs include resource requirements, basis of estimates, a resource breakdown structure, and project documents updates.
Acquiring resources includes obtaining team members, facilities, equipment, materials, supplies, and other resources as needed. Outputs include physical and project team assignments, resource calendars, change requests, and updates to several documents.

## Slide 8: Project Human Resource Management Processes
4. Developing the project team involves building individual and group skills to enhance project performance. Team-building skills are often a challenge for many project managers. The main outputs of this process are team performance assessments, change requests, and updates to several documents.
5. Managing the project team involves tracking team member performance, motivating team members, providing timely feedback, resolving issues and conflicts, and coordinating changes to help enhance project performance. Outputs of this process include change requests, project management plan updates, project documents updates, and organizational process assets updates.
6. Controlling resources ensures that a project’s physical resources are available as planned, monitoring the planned versus actual resource utilization, and taking corrective action when needed. Outputs include work performance information, change requests, and updates to the project management plan and project documents.

## Slide 9: Keys to Managing People
Psychologists and management theorists have devoted much research and thought to the field of managing people at work
Important areas related to project management include
  motivation theories
  influence and power
  Effectiveness
  Leadership
  Emotional intellegence.

## Slide 10: Intrinsic and Extrinsic Motivation
Intrinsic motivation causes people to participate in an activity for their own enjoyment
Extrinsic motivation causes people to do something for a reward or to avoid a penalty
For example, some children take piano lessons for intrinsic motivation (they enjoy it) while others take them for extrinsic motivation (to get a reward or avoid punishment)

## Slide 11: 1. Developing the Management Resource Plan
To develop a resource management plan for a project, you must identify and document project resources, roles, responsibilities, skills, and reporting relationships.
The project resource management plan can be separated into a human resource management plan and a physical resource management plan.
The human resource plan often includes an organizational chart for the project, detailed information on roles and responsibilities, and a staffing management plan. In addition, project teams can create a team charter to provide guidance on how they will operate.
Contents include
  project organizational charts
  staffing management plan
  responsibility assignment matrixes
  resource histograms

## Slide 12: Figure 9-3. Sample Organizational Chart for a Large IT Project

## Slide 13: 1.1 work definition and assignment process
In addition to defining an organizational structure for a project, it is also important to follow a work definition and assignment process. Figure 9-4 provides a framework for defining and assigning work that consists of four steps:
Finalizing the project requirements
Defining how the work will be accomplished
Breaking down the work into manageable elements
Assigning work responsibilities
The work definition and assignment process is carried out during the proposal and startup phases of a project. Note that the process is iterative, often taking more than one pass.

## Slide 14: Figure 9-4. Work Definition and Assignment Process

## Slide 15: 1.2 Organizational breakdown structure (OBS)
Once the project manager and project team have broken down the work into manageable elements, the project manager assigns work to organizational units.
The project manager often bases these work assignments on where the work fits in the organization and uses an organizational breakdown structure to conceptualize the process.
An organizational breakdown structure (OBS) is a specific type of organizational chart that shows which organizational units are responsible for which work items.
The OBS can be based on a general organizational chart and then broken down into more detail, based on specific units within departments in the company or units in any subcontracted companies. For example, OBS categories might include software development, hardware development, and training.

## Slide 16: 1.2 Responsibility Assignment Matrices
After developing an OBS, the project manager can develop a responsibility assignment matrix
A responsibility assignment matrix (RAM) is a matrix that maps the work of the project as described in the WBS to the people responsible for performing the work as described in the OBS
Can be created in different ways to meet unique project needs
For smaller projects, it is best to assign individual people to WBS activities. For very large projects, it is more effective to assign the work to organizational units or teams

## Slide 17: Figure 9-5. Sample Responsibility Assignment Matrix (RAM)

## Slide 18: 1.3 RACI chart
In addition to using a RAM to assign detailed work activities, you can use it to define general roles and responsibilities on projects. This type of RAM can include the stakeholders in the project. Some organizations use RACI charts to show four key roles for project stakeholders:
Responsibility: Who does the task?
Accountability: Who signs off on the task or has authority for it?
Consultation: Who has information necessary to complete the task?
Informed: Who needs to be notified of task status and results?

## Slide 19: Table 9-2. Sample RACI Chart
R = responsibility
A = accountability, only one A per task
C = consultation
I = informed
Note that some people reverse the definitions of responsible and accountable.

## Slide 20: 1.4 Staffing Management Plans and Resource Histograms
A staffing management plan describes when and how people will be added to and taken off the project team
For example, if an IT project is expected to need 100 people on average over a year, the staffing management plan would describe the types of people needed to work on the project, such as Java programmers, business analysts, and technical writers, and the number of each type of person needed each month. The plan would also describe how these resources would be acquired, trained, rewarded, and reassigned after the project.
A resource histogram is a column chart that shows the number of resources assigned to a project over time

## Slide 21: Figure 9-6. Sample Resource Histogram

## Slide 22: 1.4 Team Charters
Many companies believe in using team charters to help promote teamwork and clarify team communications. (Note that some organizations and previous editions of this text use the term team contract instead of team charter.
Contents of the team charter, according to PMI, may include the following:
  Team values
  Communication guidelines
  Decision-making criteria and process
  Conflict resolution process
  Meeting guidelines
  Team agreements

## Slide 23: 2. Estimating Activity Resources
The people who help determine what resources are necessary must have experience and expertise in similar projects and with the organization performing the project.
Important questions to answer when estimating activity resources include the following:
  How difficult will specific activities be on this project?
  What is the organization’s history in doing similar activities? Has the organization done similar tasks before? What level of personnel did the work?
  Does the organization have people, equipment, and materials that are capable and available for performing the work? Could any organizational policies affect the availability of resources?
  Does the organization need to acquire more resources to accomplish the work? Would it make sense to outsource some of the work? Will outsourcing increase or decrease the amount of resources needed and when they will be available?

## Slide 24: 2. Estimating Activity Resources
The main outputs of the resource estimating process include a list of activity resource requirements, a basis of estimates, a resource breakdown structure, and project documents updates.
A resource breakdown structure is a hierarchical structure that identifies the project’s resources by category and type. Resource categories might include analysts, programmers, and testers. This information would be helpful in determining resource costs, acquiring resources, and so on.

## Slide 25: 3. Acquiring resources
Today, many organizations again face a shortage of IT staff. Regardless of the current job market, however, acquiring qualified IT professionals is critical.
In addition to recruiting team members, it is also important to acquire the necessary physical resources (facilities, equipment, supplies, and so on) and provide the right type of resources at the right time and place.

## Slide 26: 3.1Resource Assignment
Organizations that do a good job of staff acquisition have good staffing plans. These plans describe the number and type of people who are currently in the organization and the number and type of people anticipated to be needed for the project based on current and upcoming activities.
An important component of staffing plans is maintaining a complete and accurate inventory of employees’ skills. If there is a mismatch between the current mix of people’s skills and needs of the organization, it is the project manager’s job to work with top management, human resource managers, and other people in the organization to address staffing and training needs.
Staffing plans and good hiring procedures are important, as are incentives for recruiting and retention
  Some companies give their employees one dollar for every hour a new person they helped hire works
  Some organizations allow people to work from home as an incentive

## Slide 27: 3.2 Resource Loading
Resource loading refers to the amount of individual resources that an existing schedule requires during specific time periods.
Project managers often use resource histograms, like the one shown in Figure 9-6, to depict period-by-period variations in resource loading. A resource histogram can be very helpful in determining resource needs or in identifying staffing problems.
Overallocation means that not enough resources are available to perform the assigned work during a given time period. Figure 9-7 shows a sample resource histogram created in Microsoft Project.

## Slide 28: Figure 9-7. Sample Histogram Showing an Overallocated Individual
Notes: This histogram illustrates how much one person, Joe Franklin, is assigned to work on the project each week. The numbers on the vertical axis represent the percentage of Joe’s available time that is allocated for him to work on the project. The top horizontal axis represents time in weeks. Note that Joe Franklin is overallocated most of the time. For example, for most of March and April and part of May, Joe’s work allocation is 300 percent of his available time. If Joe is normally available 8 hours per day, this means he would have to work 24 hours a day to meet this staffing projection!
Overallocation can happen for many reasons. Many people don’t use the resource assignment features of project management software properly. You also need to provide good estimates of how many hours are required to accomplish work. As mentioned in Chapter 6, Project Schedule Management, a typical worker does productive work between 70 and 80 percent of the time. If people are assigned to work for 40 hours in a week, you should estimate that they will accomplish 28 to 32 hours of productive work. Of course, there are exceptions to this rule of thumb, but it is unrealistic to assume that all workers are productive 100 percent of the time.

## Slide 29: 3.3 Resource Leveling
Resource leveling is a technique for resolving resource conflicts by delaying tasks
The main purpose of resource leveling is to create a smoother distribution of resource usage and reduce overallocation
Overallocation is one type of resource conflict. If a certain resource is overallocated, the project manager can change the schedule to remove resource overallocation. If a certain resource is underallocated, the project manager can change the schedule to try to improve the use of the resource.
Notes: or example, you can sometimes remove overallocations by delaying noncritical tasks, which does not result in an overall schedule delay. At other times, you will need to delay the project completion date to reduce or remove overallocations.

## Slide 30: Figure 9-8. Resource Leveling Example
Notes: Figure 9-8 illustrates a simple example of resource leveling. The network diagram at the top of this figure shows that Activities A, B, and C can all start at the same time. Activity A has a duration of two days and will take two people to complete; Activity B has a duration of five days and will take four people to complete; and Activity C has a duration of three days and will take two people to complete. The histogram in the lower-left corner of this figure shows the resource usage if all activities start on day one. The histogram in the lower-right corner shows the resource usage if Activity C is delayed two days, its total slack allowance. Notice that the lower-right histogram is flat or leveled; that is, its activities are arranged to take up the least space, saving days and number of workers. You may recognize this strategy from the computer game Tetris, in which you earn points for keeping the falling shapes as level as possible. In the same way, resources are used best when they are leveled.

## Slide 31: 3.3 Benefits of Resource Leveling
When resources are used on a more constant basis, they require less management
It may enable project managers to use a just-in-time inventory type of policy for using subcontractors or other expensive resources
It results in fewer problems for project personnel and accounting department
It often improves morale People like to have stability in their jobs. It is very stressful for people not to know what projects they will be working on from week to week or even from day to day.
Notes: First, when resources are used on a more constant basis, they require less management. For example, it is much easier to manage someone who is scheduled to work 20 hours per week on a project for the next three months than it is to manage the same person for 10 hours one week, 40 the next, 5 the next, and so on.
Second For example, a project manager might want to level resources for work that must be done by particular subcontractors such as testing consultants. This leveling might allow the project to use four outside consultants full time to perform testing for four months instead of spreading out the work over more time or using more than four people.
Third For example, if people with expertise in the same area are only assigned to a project two days a week and they need to work together, then the schedule needs to reflect this need. The Accounting department might complain when subcontractors charge a higher rate for billing less than 20 hours a week on a project. The accountants will remind project managers to strive to get the lowest rates possible.

## Slide 32: 4. Developing the Project Team
The main goal of team development is to help people work together more effectively to improve project performance
It takes teamwork to successfully complete most projects
Tools and techniques for team development, include: training, team-building activities, and reward and recognition systems.

## Slide 33: 4.2 Training
Project managers often recommend that people take specific training courses to improve individual and team development.
Training can help people understand themselves, each other, and how to work better in teams

## Slide 34: 5. Managing the Project Team
Project managers must lead their teams in performing various project activities
After assessing team performance and related information, the project manager must decide
  if changes should be requested to the project
  if corrective or preventive actions should be recommended
  if updates are needed to the project management plan or organizational process assets.
Project managers must use their soft skills to find the best way to motivate and manage each team member.

## Slide 35: 5.1 Tools and Techniques for Managing Project Teams
Observation and conversation
Project performance appraisals
Interpersonal skills
Conflict management

## Slide 36: 5.3Five Dysfunctions of a Team
Patrick Lencioni, author of several books on teams, says that “Teamwork remains the one sustainable competitive advantage that has been large untapped”*
The five dysfunctions of teams are
    Absence of trust
    Fear of conflict
    Lack of commitment
    Avoidance of accountability
    Inattention to results
*Lencioni, Patrick, “Overcoming the Five Dysfunctions of a Team,” Jossey-Bass: San Francisco, CA (2005), p. 3.

## Slide 37: 5.4General Advice on Teams
Be patient and kind with your team
Fix the problem instead of blaming people
Establish regular, effective meetings
Allow time for teams to go through the basic team-building stages
Limit the size of work teams to three to seven members

## Slide 38: 5.4 General Advice on Teams (cont’d)
Plan some social activities to help project team members and other stakeholders get to know each other better
Stress team identity
Nurture team members and encourage them to help each other
Take additional actions to work with virtual team members

## Slide 39: 6. Controlling Resources
Controlling resources involves ensuring that the physical resources assigned to the project are available as planned.
It also involves monitoring the planned versus actual resources utilization and taking corrective actions as needed.
Key outputs include work performance information, change requests, project management plan updates, and project documents updates.

## Slide 40: Using Software to Assist in Human Resource Management
Software can help in producing RAMS and resource histograms
Project management software includes several features related to human resource management such as
  Assigning resources
  Identifying potential resource shortages or underutilization
  Leveling resources

## Slide 41: Project Resource Management Involves Much More Than Using Software
People are the most important asset on most projects, and human resources are very different from other resources. You cannot simply replace people in the same way that you replace a piece of equipment.
Project managers must
  Treat people with consideration and respect
  Understand what motivates them
  Communicate carefully with them