## Slide 1
ARCH 435 PROJECT MANAGEMENT
Lecture 3: Project Time Planning
(Arrow Diagramming Technique)
Activity on Arrow (AOA)

## Slide 2
Each activity (task) is portrayed or presented by an arrow.
The tail and head of the arrow denote the start and finish of the activity whilst its duration is shown in brackets below.
The length of the arrow has no significance neither has its orientation.
ARROW DIAGRAM
Activity
] Duration]
Site Preparation
] 30]

## Slide 3
As means of further defining the point in time, when an activity starts or finishes, start and finish events are added.
An event (= node = connector), unlike an activity, does not consume time or resources, it merely represents a point in time at which something happens.
Numbers are given to the events to provide a unique identity to each activity.
The first event in a project schedule is the start of the project. The last event in a project schedule is the end of the project.
ARROW DIAGRAM

## Slide 4
20
10
Activity
[Duration]
Start Event
Finish Event
Activity identification numbers
called event numbers
Activity Identification

## Slide 5
i-j Numbers of Events
The node at the tail of an arrow is the i-node.
The node at the head of an arrow is the j-node.
i
j
Activity
Duration

## Slide 6
The network (the graphical representation of a project plan) must have definite points of beginning and finish.
(The accuracy and usefulness of a network is dependent mainly upon intimate knowledge of the project itself, and upon the general qualities of judgment and skill of the planning personnel.)
The arrows originate at the right side of a node and terminate at the left side of a node.
Any two events may be directly connected by no more than one activity.
Use symbols to indicate crossovers to avoid misunderstanding.
Rules of Making Arrow Diagram

## Slide 7
20
10
30
A
B
Logical Relationships
Node “20” is the j-node for activity “A” and it is also the i-node for activity “B”. Therefore, activity “A” is a predecessor to activity “B”.
In other words activity “B” is a successor to activity “A”.
Activity B depends on activity A.

## Slide 8
20
10
40
30
50
Succeeding activities
Event numbers must not be duplicated in a network.
j-node number is always greater than i-node number.
Logical Relationships

## Slide 9
Concurrent activities (happens at the same time)
80
120
160
170
180
190
Logical Relationships

## Slide 10
The network must be a logical representation of all the activities. Dummy Activities are used, where necessary for:
  Unique numbering, and
  Logical sequencing.
  Dummy activity is an arrow that represents merely a dependency of one activity upon another. A dummy activity has a zero time. It is also called dependency arrow.
Rules of Making Arrow Diagram

## Slide 11
The following network shows incorrect activity numbering.
90
100
110
50
70
60
80
A
B
Dummy Activities

## Slide 12
For unique numbering, use a dummy activity.
90
100
110
50
70
60
80
A
B
75
Dummy Activities

## Slide 13
50
30
10
40
20
For representing logical relationships,
you may need dummy activities.
Dummy Activities
A
B
C
D
In this diagram:
Activity C depends on Activities A, B.
Activity D depends on Activities A, B.
LETS SAY, Activity C depends on Activity A ONLY, and Activity D depends on Activities A, B. How can we represent this relationship?

## Slide 14
50
30
10
40
20
In this case, use a dummy activity to indicate the correct relationship.
Dummy Activities
A
B
C
D
Now,
Activity C depends on Activities A ONLY.
Activity D depends on Activities A, B.
35

## Slide 15
There must be no "looping" in the network. The loop is an indication of faulty logic. The definition of one or more of the dependency relationships is not valid.
Rules of Making Arrow Diagram
130
120
100
90
110

## Slide 16
The network must be continuous (without unconnected activities).
80
100
60
30
90
50
20
10
120
110
70
40
Rules of Making Arrow Diagram

## Slide 17
Networks should have only one initial event and only one terminal event.
60
30
90
50
20
10
120
110
70
40
Rules of Making Arrow Diagram

## Slide 18
Before an activity may begin, all activities preceding it must be completed (the logical relationship between activities is (finish to start).
Rules of Making Arrow Diagram

## Slide 19
Standard layout for recording data
Network Analysis (Computation)
Occurrence times of Events = Early and late timings of event occurrence = Early and late event times
Earliest
Event
Time
Latest
Event
Time
Event
Label
Activity
Tail
Head
Activity

## Slide 20
Early Event Time (EET = E =TE)
Forward Pass for Computing EET
Each activity starts as soon as possible, i.e., as soon as all of its predecessor activities are completed.
Direction: Left to right, from the beginning to the end of the project
Set: EET of the initial node = 0
Add: EETj = EETi + Dij
Take the maximum
The estimated project duration = EET of the last node.
Early Event Time (Earliest occurrence time for event) is the earliest time at which an event can occur, considering the duration of precedent activities.
j
i
EETj
EETi
Activity
Dij

## Slide 21
0
1
10
20
3
3
A
B
8
30
4
C
40
12
Early Event Times (EET = E =TE)

## Slide 22
Early Event Times (TE)
12
40
80
4
5
9
K
L
M
50
15
70
24
4

## Slide 23
Early Event Times (TE) Example:
20
10
30
50
40
60
70
2
3
3
4
3
1
5
4
7

## Slide 24
Early Event Times (TE)
20
10
0
30
50
40
3
60
70
2
3
3
4
3
1
5
4
7
9
16
8
2
4

## Slide 25
Late Event Time (LET = L =TL)
Backward Pass for Computing LET
Direction: Right to left, from the end to the beginning of the project
Set: LET of the last (terminal) node = EET .
Subtract: LETi = LETj - Dij
Take the minimum
Late Event Time (Latest occurrence time of event) is the latest time at which an event can occur, if the project is to be completed on schedule.
j
i
LETi
EETj
LETj
EETi
Activity
Dij

## Slide 26
Late Event Times (TL)
8
13
50
16
16
3
7
40
60
9
9

## Slide 27
2
20
10
0
4
30
50
3
60
70
2
3
3
4
3
1
5
4
7
9
16
8
40
Late Event Times (TL), Example:

## Slide 28
2
20
10
0
4
30
50
40
3
60
70
2
3
3
4
3
1
5
4
7
9
16
8
16
13
9
10
4
8
0
Late Event Times (TL), Example:

## Slide 29
Early Start (ES): The earliest time at which an activity can be started.
ESij = EETi
Early Finish (EF): The earliest time at which an activity can be completed.
EFij = ESij + Dij
Late Finish (LF): The latest time at which an activity can be completed without delaying project completion.
LFij = LETj
Late Start (LS): The latest time at which an activity can be started.
LSij = LFij  Dij
Activity Times (Schedule)
Network Analysis (Computation)

## Slide 30
Example: Activity Times
2
20
10
0
4
30
50
40
3
60
70
2
3
3
4
3
1
5
4
7
9
16
8
16
13
9
10
4
8
0
ES20-50 = EET20 = 2
EF20-50 = ES + D = 2 + 3 = 5
LF20-50 = LET50 = 13
LS20-50 = LF – D = 13 – 3 = 10

## Slide 31
Total Float (TF)
Total float or path float is the amount of time that an activity’s completion may be delayed without extending project completion time.
Total float or path float is the amount of time that an activity’s completion may be delayed without affecting the earliest start of any activity on the network critical path.
Activity Floats
Network Analysis (Computation)

## Slide 32
Total Float (TF)
Total path float time for activity (i-j) is the total float associated with a path.
For arbitrary activity (ij), the total float can be written as:
Path Float =Total Float (TFij)
= LSij  ESij
= LFij  EFij
= LETj – EETi  Dij
Activity Floats
Network Analysis (Computation)

## Slide 33
Example: Total Float Times
TF20-50 = LS20-50 - ES20-50
TF20-50 = 10 – 2 = 8
TF20-50 = LF20-50 - EF20-50
TF20-50 = 13 – 5 = 8
TF20-50 = LET50 – EET20 - D20-50
TF20-50 = 13 – 2 – 3 = 8
2
20
10
0
4
30
50
40
3
60
70
2
3
3
4
3
1
5
4
7
9
16
8
16
13
9
10
4
8
0

## Slide 34
Network Analysis (Computation)
Free Float (FF)
  Free float or activity float is the amount of time that an activity’s completion time may be delayed without affecting the earliest start of succeeding activity.
  Activity float is “owned” by an individual activity, whereas path or total float is shared by all activities along a slack path.
  Total float always equals or exceeds free float (TF ≥ FF).
  For arbitrary activity (ij), the free float can be written as:
Activity Float = Free Float (FFij)
= ESjk  EFij
= EETj – EETi  Dij
Activity Floats

## Slide 35
FF20-50 = ES50-70 – EF20-50
FF20-50 = 8 – 5 = 3
FF20-50 = EET50 – EET20 - D20-50
FF20-50 = 8 – 2 – 3 = 3
Example: Free Float Times
2
20
10
0
4
30
50
40
3
60
70
2
3
3
4
3
1
5
4
7
9
16
8
16
13
9
10
4
8
0

## Slide 36
Network Analysis (Computation)
Interfering Float (ITF)
  Interfering float is the difference between TF and FF.
  If ITF of an activity is used, the start of some succeeding activities will be delayed beyond its ES.
  In other words, if the activity uses its ITF, it “interferes” by this amount with the early times for the down path activity.
  For arbitrary activity (ij), the Interfering float can be written as:
Interfering Float (ITFij)
= TFij  FFij
= LETj  EETj
Activity Floats

## Slide 37
ITF20-50 = TF20-50 - FF20-50
IFF20-50 = 8 – 3 = 5
ITF20-50 = LET50 – EET50
ITF20-50 = 13 – 8 = 5
Example: Interfering Float Times
2
20
10
0
4
30
50
40
3
60
70
2
3
3
4
3
1
5
4
7
9
16
8
16
13
9
10
4
8
0

## Slide 38
Network Analysis (Computation)
Independent Float (IDF)
  It is the amount of float which an activity will always possess no matter how early or late it or its predecessors and successors are.
  The activity has this float “independent” of any slippage of predecessors and any allowable start time of successors. Assuming all predecessors end as late as possible and successors start as early as possible.
  IDF is “owned” by one activity.
  In all cases, independent float is always less than or equal to free float (IDF ≤ FF).
Activity Floats

## Slide 39
Network Analysis (Computation)
Independent Float (IDF)
  For arbitrary activity (ij), the Independent Float can be written as:
Independent Float (IDFij)
= Max (0, EETj  LETi – Dij)
= Max (0, Min (ESjk) - Max (LFli)  Dij)
Activity Floats

## Slide 40
Example: Independent Float Times
IDF20-50 = Max. (0, [EET50 – LET20 - D20-50])
IDF20-50 = Max. (0, [8 – 10 – 3]) = 0
2
20
10
0
4
30
50
40
3
60
70
2
3
3
4
3
1
5
4
7
9
16
8
16
13
9
10
4
8
0