## Slide 1: Introduction to MS Project 2007
Tutorial 2
Instructor: Hanif Ullah
Email ID: hanif.ksu@hotmail.com
Office #: 2029
Date: 19/02/2012

## Slide 2: MS Project 2007 Family
Microsoft Office Project Standard 2007 Windows-based desktop application for project management. The Standard edition is designed for the single project manager and does not interact with Project Server.
Microsoft Office Project Professional 2007 Windows-based desktop application that includes the complete feature set of the Standard edition, plus-when used with Project Server-additional project team planning and communications features. Project Professional plus Project Server represents Microsoft’s enterprise project management (EPM) product offering.
Microsoft Office Project Server 2007 Intranet-based solution that enables enterprise-level project collaboration, timesheet reporting, and status reporting when used in conjunction with Project Professional.
Microsoft Office Project Web Access 2007 Internet Explorer-based interface for working with Project Server.
Microsoft Office Project Portfolio Server 2007 Portfolio management solution.
In this Lab we will be using and practicing only Microsoft Office Project Professional 2007.

## Slide 3: Starting Project Professional
In this exercise, you’ll start Project Professional

## Slide 4: Creating a New Project Plan
On the File menu, click the New command. Then, in the New Project task pane, click Blank Project.
Project creates a new, blank project plan. Next, you’ll set the project’s start date.
On the Project menu, click Project Information.
The Project Information dialog box appears.
In the Start date box, type or select current date.
Click OK to close the Project Information dialog box
On the Standard toolbar, click the Save button
In the File name box, type Wingtip Toys Commercial 1.
Click Save to close the Save As dialog box

## Slide 5: Setting Nonworking Days
On the Tools menu, click Change Working Time
The Change Working Time dialog box appears
In the For calendar box, click the down arrow
24 Hours: Has no nonworking time.
Night Shift: Covers a “graveyard” shift schedule of Monday night through Saturday morning, 11 P.M. to 8 A.M., with a one-hour break.
Standard: The traditional working day, Monday through Friday from 8 A.M. to 5 P.M., with a one-hour lunch break.
For this project, you’ll use the Standard base calendar as the project calendar, so leave it selected

## Slide 6: Setting Nonworking Days
In the Name field on the Exceptions tab, type Staff at morale event, and then click in the Start field
In the Start field, enter the desired non-working day/days.
Click OK to close the Change Working Time dialog box

## Slide 7: Creating a Task List
Tasks are the most basic building blocks of any project-tasks represent the work to be done to accomplish the goals of the project. Tasks describe project work in terms of sequence, duration, and resource requirements.
Types of Tasks:
  summary tasks (which summarize or “roll up” the durations, costs, and so on of subtasks)
  milestones (which indicate significant events in the life of a project).
In the first cell directly below the Task Name column heading, type Pre-Production, and then press Enter
Enter the following task names below the Pre-Production task name, pressing Enter after each task name

## Slide 8: Creating a Task List
Develop script
Develop production boards
Pick locations
Hold auditions
Production
Rehearse
Shoot video
Log footage

## Slide 9: Estimating Durations
A task’s duration is the amount of time you expect it will take to complete the task.
When working in Project, you can use the following abbreviations for duration.
If you enter this abbreviation | It appears like this | And it means
m | min | minute
h | hr | hour
d | day | day
w | wk | week
mo | mon | month

## Slide 10: Entering Durations
Click the cell below the Duration column heading for task 2, Develop script.
The Duration field for task 2 is selected.
Type 5d, and then press Enter .
The value 5 days appears in the Duration field.

## Slide 11: Entering Durations
Enter the following durations for the remaining tasks.
Task ID | Task Name | Duration
3 | Develop production boards | 3d
4 | Pick locations | 2d
5 | Hold auditions | 2d
6 | Production | (Press Enter to skip this task for now)
7 | Rehearse | 2d
8 | Shoot video | 2d
9 | Log footage | 1d

## Slide 12: Entering a Milestone
Milestones are significant events that are either reached within the project (such as completion of a phase of work) or imposed upon the project (such as a deadline by which to apply for funding).
Click the name of task 6, Production.
On the Insert menu, click New Task.
Type Pre-Production complete! and then press the tab key to move to the Duration field
In the Duration field, type 0d and then press the Enter key. The milestone is added to your plan.

## Slide 13: Organizing Tasks into Phases
It is helpful to organize groups of closely related tasks that represent a major portion of the project’s work into phases
For example, it is common to divide a film or video project into major phases of work such as pre-production, production, and post-production. You create phases by indenting and outdenting tasks.
A summary task behaves differently from other tasks. You can’t edit its duration, start date, or other calculated values directly because this information is derived or “rolled up” from the detail tasks, called subtasks (these appear indented under the summary tasks). Project calculates the duration of a summary task as the span of time from the earliest start date to the latest finish date of its subtasks.

## Slide 14: Creating Summary Tasks
In this exercise, you create two summary tasks by indenting tasks.
Select the names of tasks 2 through 6.
click the Indent Tasks button on the Formatting toolbar.
Task 1 becomes a summary task. A summary task bar for it appears in the Gantt chart, and the summary task name is formatted in bold type.
Next, select the names of tasks 8 through 10.
4. On the Project menu, point to Outline, and then click Indent.
Task 7 becomes a summary task, and a summary task bar for it appears in the Gantt chart.

## Slide 15
END of Tutorial 2