## Slide 1: Essentials of Systems Analysis and Design Fourth Edition Joseph S. Valacich Joey F. George Jeffrey A. Hoffer
Chapter 3
Managing the Information Systems Project
3.1

## Slide 2: Managing the Information Systems Project
Focus of Project Management
  To assure that information system projects meet customer expectations
    Delivered in a timely manner
    Meet constraints and requirements
3.2

## Slide 3: Managing the Information Systems Project (continued)
Project Manager
  Systems Analyst responsible for
    Project initiation
    Planning
    Execution
    Closing down
  Requires diverse set of skills
    Management
    Leadership
    Technical
    Customer relations
3.3

## Slide 4: Project Management Process
Project
  Planned undertaking of related activities to reach an objective that has a beginning and an end
Four Phases
  Initiating
  Planning
  Executing
  Closing down
3.4

## Slide 5: Initiating the Project
The first phase of the project management process in which activities are performed to assess the size, scope, and complexity of the project and to establish procedures to support later project

## Slide 6: Initiating the Project
Establish the project initiation team
Establish a relationship with the customer
Establish the project initiation plan
Establish management procedures
Establish the project management environment and workbook
Project workbook: An on-line or hard-copy repository for all project correspondence, inputs, outputs, deliverables, procedures, and standards used by all team members useful for project audits, orientation of new team members and performing post project reviews.
3.6

## Slide 7: Planning the Project
Describe project scope, alternatives and feasibility
  Scope and Feasibility
    Understand the project
    What problem is to be addressed
    What results are to be achieved
    Measures of success
    Completion criteria
Divide the project into manageable tasks
    Work breakdown structure : The process of dividing the project into manageable tasks and logically ordering them to ensure a smooth evolution between tasks
    Gantt chart
3.7

## Slide 8: Planning the Project (continued)
Estimate resources and create a resource plan.
Develop a preliminary schedule
    Utilize Gantt Charts and Network Diagrams
Develop a communication plan
  Outline communication processes among customers, team members and management
  Define types of reports and their distribution
3.8

## Slide 9: Planning the Project (continued)
Determine project standards and procedures
  Specify how deliverables are tested and produced
Identify and assess risk
  Identify sources of risk
  Estimate consequences of risk
Create a preliminary budget
3.9

## Slide 10: Planning the Project (continued)
Develop a project scope statement
  Describe what the project will deliver
Set a baseline project plan
  Estimate of project’s tasks and resources
3.10

## Slide 11: Executing the Project
Execute baseline project plan
  Acquire and assign resources
  Train new team members
  Keep project on schedule
Monitor project progress
  Adjust resources, budget, and/or activities
3.11

## Slide 12: Executing the Project (continued)
Manage changes to baseline project plan
  Slipped completion dates
  Bungled activity that must be redone
  Changes in personnel
  New activities
Maintain project workbook
Communicate project status
3.12

## Slide 13: Closing Down the Project
Termination
  Types of termination:
    Natural
      Requirements have been met
    Unnatural
      Project stopped
  Documentation
  Personnel Appraisal
3.13

## Slide 14: Closing Down the Project (continued)
Conduct post-project reviews
  Determine strengths and weaknesses of
    Project deliverables
    Project management process
    Development process
Close customer contract
3.14

## Slide 15: Representing and Scheduling Project Plans
Gantt Charts
  Gantt chart: A graphical representing of a project showing each task as a horizontal bar whose length is proportional to its time for completion.
  Gantt charts do not show how tasks must be ordered but simply shows when an activity must begin and end.
  Useful for depicting simple projects or parts of large projects
  Show start and completion dates for individual tasks
Network Diagrams
  Show order of activities
3.15

## Slide 16
3.16

## Slide 17: Representing Project Plans
Network diagramming is a critical path scheduling technique
Used when tasks
  Are well-defined and have a clear beginning and end point
  Can be worked on independently of other tasks
  Are ordered
  Serve the purpose of the project
Major strength is ability to show how completion times vary by activity
3.17

## Slide 18: Commercial Project Management Software
Many systems are available
Three activities are required:
  Establish project start or end date
  Enter tasks and assign task relationships
  Select scheduling method to review project reports
3.18

## Slide 19: Summary
Skills of An Effective Project Manager
Activities of Project Manager
  Initiation
  Planning
  Execution
  Close down
Gantt Charts and Network Diagrams
Commercial PM Software
3.19