## Slide 1: ENGINEERING MANAGEMENT (GE 404)
Tutorial # 2
Activity on Node
بسم الله الرحمن الرحيم
Instructor: Eng.Alothman
Notes: This is a title slide.

## Slide 2: Activity on Node
ADVANTAGES:
Precedence relationships
Time calculation
large projects
more efficient

## Slide 3
EXAMPLE 1:
Draw activity on node diagram for the following project
Activity | Predecessor | Duration (weeks)
A | - | 12
B | A | 16
C | A | 8
D | A | 18
E | B , C | 8
F | D , E | 10
A
C
E
F
B
D
ES | D | EF
 | Act | FF
LS | TF | LF
 | 12 | 
 | A | 
 | 16 | 
 | B | 
 | 8 | 
 | C | 
 | 18 | 
 | D | 
 | 8 | 
 | E | 
 | 10 | 
 | F | 

## Slide 4
ES | D | EF
 | Act | FF
LS | TF | LF
Times Calculations
1- EF = ES + D
2- LS = LF - D
3- Total float (TF) = LS - ES = LF - EF
    4- Free Float (FFi ) = Min. (ESj) - EFi
0 | 12 | 12
 | A | 0
0 | 0 | 12
12 | 16 | 28
 | B | 0
12 | 0 | 28
12 | 8 | 20
 | C | 8
20 | 8 | 28
12 | 18 | 30
 | D | 6
18 | 6 | 36
28 | 8 | 36
 | E | 0
28 | 0 | 36
36 | 10 | 46
 | F | 0
36 | 0 | 46
Project Duration: 46 weeks
Critical Path : A-B-E-F
Largest EF
Smallest LSj
0 | 12 | 12
 | A | 0
12 | 16 | 28
 | B | 0
12 | 8 | 20
 | C | 8
12 | 18 | 30
 | D | 6
28 | 8 | 36
 | E | 0
36 | 10 | 46
 | F | 0

## Slide 5
Times Calculations Summary
Activity | Predecessor | Duration (weeks) | ES | EF | LS | LF | FF | TF
A | - | 12 | 0 | 12 | 0 | 12 | 0 | 0
B | A | 16 | 12 | 28 | 12 | 28 | 0 | 0
C | A | 8 | 12 | 20 | 20 | 28 | 8 | 8
D | A | 18 | 12 | 30 | 18 | 36 | 6 | 6
E | B , C | 8 | 28 | 36 | 28 | 36 | 0 | 0
F | D , E | 10 | 36 | 46 | 36 | 46 | 0 | 0
ES | D | EF
 | Act | FF
LS | TF | LF

## Slide 6
Example 2:
Draw activity on node diagram for the following project
Activity | Predecessor | Duration(weeks)
A | - | 20
B | A | 8
C | A | 6
D | B | 12
E | C | 16
F | C | 18
G | D | 16
H | D , E, F | 8
I | F | 10
J | G , H , I | 10
A
C
J
B
E
D
F
H
G
I

## Slide 7
 | 20 | 
 | A | 
 | 6 | 
 | C | 
 | 16 | 
 | E | 
 | 8 | 
 | H | 
 | 10 | 
 | J | 
 | 8 | 
 | B | 
 | 12 | 
 | D | 
 | 16 | 
 | G | 
 | 18 | 
 | F | 
 | 10 | 
 | I | 
ES | D | EF
 | Act | FF
LS | TF | LF

## Slide 8
0 | 20 | 20
 | A | 0
0 | 0 | 20
20 | 6 | 26
 | C | 0
22 | 2 | 28
26 | 16 | 42
 | E | 2
32 | 6 | 48
44 | 8 | 52
 | H | 4
48 | 4 | 56
56 | 10 | 66
 | J | 0
56 | 0 | 66
20 | 8 | 28
 | B | 0
20 | 0 | 28
28 | 12 | 40
 | D | 0
28 | 0 | 40
40 | 16 | 56
 | G | 0
40 | 0 | 56
26 | 18 | 44
 | F | 0
28 | 2 | 46
44 | 10 | 54
 | I | 2
46 | 2 | 56
PROJECT DURATIN: 66 weeks
CRITAL PATH : A-B-D-G-J
ES | D | EF
 | Act | FF
LS | TF | LF
Times Calculations
1- EF = ES + D
2- LS = LF - D
3- Total float (TF) = LS - ES = LF - EF
    4- Free Float (FFi ) = Min. (ESj) - EFi

## Slide 9
ES | D | EF
 | Act | FF
LS | TF | LF
Times Calculations Summary
Activity | Predecessor | Duration (weeks) | ES | EF | LS | LF | FF | TF
A | - | 20 | 0 | 20 | 0 | 20 | 0 | 0
B | A | 8 | 20 | 28 | 20 | 28 | 0 | 0
C | A | 6 | 20 | 26 | 22 | 28 | 0 | 6
D | B | 12 | 28 | 40 | 28 | 40 | 0 | 0
E | C | 16 | 26 | 42 | 32 | 48 | 2 | 6
F | C | 18 | 26 | 44 | 28 | 46 | 0 | 2
G | D | 16 | 40 | 56 | 40 | 56 | 0 | 0
H | D , E, F | 8 | 44 | 52 | 48 | 56 | 4 | 4
I | F | 10 | 44 | 54 | 46 | 56 | 2 | 2
J | G , H , I | 10 | 56 | 66 | 56 | 66 | 0 | 0

## Slide 10: Thank You
Questions Please