## Slide 1: ENGINEERING MANAGEMENT (GE 404)
Lecture #11
Project Time-Control
بسم الله الرحمن الرحيم
Notes: This is a title slide.

## Slide 2: Contents
Objectives of the present lecture
Introduction to Project time-control
Process of Project time-control
Network updating (rescheduling)
Problem
Further reading

## Slide 3: Objectives of the Present lecture
To discuss process involved in project time-control
To explain how to carry out project rescheduling (or Network updating)

## Slide 4: Project Time-Control
Project time-control can be reduced to two basic components:
Monitoring
  Monitoring consists of a means of understanding what is happening on a project, obtaining information about the project by some means
Control
  Control consists of action taken in response to the information
Notes: Trade-off (between something and something) the act of balancing two things that are opposed to each other
a trade-off between increased production and a reduction in quality

## Slide 5: Process of Project Time-Control
Establish an operational schedule
Measure the progress and report the progress
Compare actual achievement with planned
Check and analyze time progress and determine effect on completion date and milestones
Plan for corrective action
Implement corrective action
Update operational schedule

## Slide 6: Establish Operational Schedule
For project control purposes a hierarchy of schedules may be needed, depending on who will use it
Key Dates Schedule
For owners and top-level management in terms of MILESTONES or KEY DATES.
Detailed Schedule
For engineers, work supervisors, material suppliers and subcontractors
A schedule of that particular engineer/supervisor work responsibility
Provide him with a day-to-day forecast of field operations
Critical activities and free float values should be noted
Covers limited time spans (2 weeks or 30 days)
Tabular listings and computer-printed bar charts are common forms

## Slide 7: Measure and Report Progress
Methods:
Estimated number of working days required to complete the activity
Estimated % completion of the activity
Quantities of work units put in place
Equations
Based on the assumption of straight-line variation between time and work accomplishment
Working days to complete = d (1 - P/100)
Working days to complete = d (1 – (W/T))
  d= total activity duration in working days
  P = estimated percentage of completion
  W= number of work units put into place
  T= total number of work units associated with the activity

## Slide 8: Contd.
Weekly Progress reports
  A common procedure in many industries
  Listing those activities that started, finished, or were in progress during the week and indicating their stages of completion
  Must include procurement, material delivery information etc.
  Chose a cutoff date, to be selected to serve both time management and labor cost accounting

## Slide 9: Contd.
WEEKLY PROGRESS REPORT Project: Highway bridge Week ending: Wednesday, July 21 (working day 27) Job. No: 7903-50 Prepared by: K.M. |  |  |  |  | 
Activity | Activity Number | Date Started | Date Completed | Percent Complete | Working days to complete
A | 110 | - | July 15 | 100 | 0
B | 115 | - | - | - | 13
C | 130 | - | - | 80 | 2
D | 150 | July 15 | July15 | 100 | 0
E | 160 | July 16 | July 21 | 100 | 0

## Slide 10: Contd.
Field Progress Narrative
To accompany weekly progress reporting
Discussion of projected project features
General statement about time status
Critical or low float activities in difficulty
Potential trouble spots
Exceptionally well project areas

## Slide 11: Compare and Analysis of Project Progress
Concerned primarily with determining the effect of the latest information on the project completion date and any milestone goals
  1st - A quick and simple check for critical activities status
  2nd - Check the possibility of a new critical path
Signs of Danger
Activities fall behind LS schedule
Resource availability delays
Realizing that time duration of future activities have been materially underestimated
Change logic becomes necessary

## Slide 12: Corrective Actions
When there are small delays that are within network time contingency, no action is usually required
Otherwise use Time Reduction Technique to bring project back on schedule
Make periodic (Weekly, biweekly, or monthly) job progress meetings with project managers, field supervisors, major subcontractors, material suppliers, and owner representative to enhance time management efficiency

## Slide 13: Network Updating (Rescheduling)
Concerned with determining the effect of schedule deviations and plan changes on the portions of the project yet to be constructed
This requires making necessary network corrections and re-computing activity times and float times
Information required for Rescheduling
  New activities to be added
  Existing activities to be deleted
  Changes in the resource availability and delivery dates
  Changes in the job logic
  New estimate of the time (for completing unfinished activities)
  Changes in the scope of work etc.

## Slide 14: Problem-1
The initial AON diagram for a small engineering project is shown below with its planned activity times in days. At the end of the 15th day, the field progress report gives you the following information:
Activity “A” was completed on schedule
Activity “B” started as planned but four days were lost due to waiting for the required resources
Activity “C” was completed one day earlier
The remaining duration of Activity “D” is 2 days
The duration of activity “H” will be reduced to 12 days instead of 17 days.
The activity “F” cannot start until the morning of day 22
Activity “Z” is expected to take two days more
Due to owner requirement the volume of work of activity “X” will be increased by 50%
Construct the updated AON diagram, calculate the early and late start times of each activity, and indicate the critical path.

## Slide 15: Solution
Note: For activity E: 13-5-18 is changed to 15-3-18
ES is changed from 13 to 15 because the current date of rescheduling is Day 15
Duration is changed from 5 to 3 because EF = 18 has to be maintained
Note: In duration cell, mention the time required/ remained w.r.t. date of reporting.

## Slide 16: Further Reading
Jimmie W. Hinze. “Construction Planning and Management,” Fourth Edition, 2012, Pearson.
Read more about the Project Monitoring and Control from:

## Slide 17: Thank You
Questions Please