## Slide 1: ENGINEERING MANAGEMENT (GE 404)
Lecture #5
Scheduling Networks—Precedence Diagramming
بسم الله الرحمن الرحيم
Notes: This is a title slide.

## Slide 2: Objectives of the Present lecture
To explain how to draw Precedence network diagrams
To discuss how to calculate Early/Late Start/Finish Times in Precedence Network diagrams

## Slide 3: Precedence Diagramming
Precedence diagramming is an extension to the original Activity-On-Node concept.
Precedence diagramming includes precedence relationships among the activities.
In addition, one may specify a “lag time” associated with any of the precedence relationships.
A successor "lags" a predecessor, but a predecessor "leads" a successor.
Lag time can be designated on a dependency line with a positive, negative, or zero value.
The prime relationship used in PERT/CPM network is Finish-to-start type of dependency, with FSij = 0 .
Notes: synonym priority
Program Evaluation Review Technique (PERT)
Time-lag: the period of time between two closely related events, phenomena, etc.,

## Slide 4: Activity Relationships
Finish-to-Start (FS)
  In a finish-to-start relationship, the start of an activity depends on the completion of its preceding activity.
  Example: Footing excavation must be completed prior to placing concrete for the footing
Start-to-Start (SS)
  In a start-to-start relationship, an activity can not start before its preceding activity starts
  Example: Project management activities can not start before the Project work starts
Finish-to-Finish (FF)
  In a finish-to-finish relationship, the two activities are related by the fact that they must be completed at the same time
  Example: In a simple task of setting a flagpole, the backfilling task and the positioning the pole task will be finished at the same time.
Start-to-Finish (SF)
  In start-to-finish relationship, the finish of an activity depends on the start of its preceding activity (A rare relationship)
  Example: In a Hospital emergency, the previous shift can not finish before the new shift starts
  Say you’re building a new gas pipeline. You would first finish construction and implementation of the new pipeline before you would begin shutting down and breaking down the old pipeline.
Notes: A: Starting of a New Bridge
B: Shutting down of an Old Bridge

## Slide 5: Lag
The amount of time that exists between the early finish of an activity and the early start of a specified succeeding activity
Calculate lags for each link by determining the difference between the ES of each activity following a link line and the EF of the activity that precedes it
Limitations and Disadvantages of Lag:
  Lag would complicate the scheduling process
  Lags are not extensively used except where the time effects are substantial for special project type

## Slide 6: Finish-to-Start Activity Precedence Relationships with Lag Values
Activity i
Activity j
Activity k
FSij
FSjk
Notes: ES is to be estimated from forward pass (That is ES of j is to be estimated by EF of i)
LF is to be estimated from backward pass (LF of i is to be estimated by LS of j)

## Slide 7: Start-to-Start Activity Precedence Relationships with Lag Values
Activity i
Activity j
Activity k
SSij
SSjk

## Slide 8: Finish-to-Finish Activity Precedence Relationships with Lag Values
Activity i
Activity j
Activity k
FFij
FFjk

## Slide 9: Start-to-Finish Activity Precedence Relationships with Lag Values
Activity i
Activity j
Activity k
SFij
SFjk

## Slide 10: Note on SFij
  Activity j cannot finish till i starts (rare)
  SFij is equal to the minimum number of time units that must transpire from the start of the predecessor i to the completion of the successor j.
Example
For the shown diagram calculate total lag if
SFij' |  |  | 
 |  | i | 
 | j |  | 
 |  | SFij'' | 
The finish of j must lag 10 units after the start of i

## Slide 11: Summary
Finish-to-Start Relationships with Lag Values FSij :
Start-to-Start Relationships with Lag Values SSij :
Finish-to-Finish Relationships with Lag Values FFij :
Start-to-Finish Relationships with Lag Values SFij :

## Slide 12: Generalized Equations
FORWARD PASS COMPUTATIONS
BACKWARD PASS COMPUTATIONS

## Slide 13: Composite Start-to-Start and Finish-to-Finish (ZZij)Activity Precedence Relationships with Lag Values
ZZij is a combination of two constraints, i.e., a start-to-start and finish-to-finish relationship. It is written with the SSij time units first, followed by the FFij time units.
Example: ZZij =5, 6
The start of activity j must lag 5 units after the start of activity i & The finish of activity j must lag 6 units after the finish of activity i

## Slide 14: Representation
ES | Duration | EF
Activity (i) |  | 
LS | Total Float | LF
ES | Duration | EF
Activity (j) |  | 
LS | Total Float | LF
Constraints with lag/lead Durations

## Slide 15: Free and Total Floats in Overlapping Networks
Free Float of an activity can be defined as time span in which the completion of the controlling date of an activity may occur and not delay the termination of the project nor delay the early status of the following activity.
Total float (TF) equation is same as it was developed for the single relationship network.

## Slide 16: Problem-1
For the given precedence diagram, complete the forward and backward pass calculations. Assume the project starts at T=0, and no splitting on activities is allowed. Also assume that the project latest allowable completion time (project duration) is scheduled for 30 working days.
FS 0
SS 3
FF 4
SS 6
SF 12
FS 0
A
Develop system spec.
(D=8)
C
Collect system data
(D=4)
D
Test & debug program
(D=6)
E
Run program
(D=6)
F
Document program
(D=12)
B
Write comp. program
(D=12)
EF | D |  | ES
Activity ID |  |  | 
LF | TF | LS | 

## Slide 17: Solution Step-1: Network diagram
A
8
B
12
D
6
C
4
END
0
E
6
F
12
EF | D |  | ES
Activity ID |  |  | 
LF | TF | LS | 

## Slide 18: Step-2: Forward Pass Computations
Activity A
Activity B
Activity C

## Slide 19
Activity D
Activity E
Activity F

## Slide 20: Contd.
A
8
B
12
D
6
C
4
END
0
E
6
F
12
0
8
3
15
9
13
15
21
21
27
15
27
27
27
FS 0
SS 3
FF 4
SS 6
SF 12
FS 0
Notes: Note: In the forward pass calculation, only you have to use logic or formulas to calculate ES. EF will be ES+D.

## Slide 21: Step-3 Backward Pass Computations
Activity F
Activity E
Activity D
A
8
B
12
D
6
C
4
END
0
E
6
F
12
0
8
3
15
9
13
15
21
21
27
15
27
27
27
30
30
3
30
30
18
3
24
3
24
18
3
FS 0
SS 3
FF 4
SS 6
SF 12
FS 0

## Slide 22
Activity C
Activity B
Activity A
A
8
B
12
D
6
C
4
END
0
E
6
F
12
0
8
3
15
9
13
15
21
21
27
15
27
27
27
30
30
3
30
30
18
3
24
3
24
18
3
18
14
5
18
6
3
11
3
3
FS 0
SS 3
FF 4
SS 6
SF 12
FS 0

## Slide 23: Step 4: Slack time (Float time)
Earliest Earliest Latest Latest On Start Finish Start Finish Slack Critical Activity ES EF LS LF LS – ES Path
A 0 8 3 11 3 Yes
B 3 15 6 18 3 Yes
C 9 13 14 18 5 No
D 15 21 15 21 3 Yes
E 21 27 24 30 3 Yes
F 15 27 18 30 3 Yes
  Critical path is the path with the least total float = The longest path through the network.
CP1: A-B-D-E, CP2: A-B-D-F ;
Critical Activities: A, B, D, E, and F

## Slide 24: Problem-2
Given the precedence network for a small engineering project with activity durations in working days, it is required to compute the activity times (ES, EF, LS, and LF) and total floats (TF) and then indicate the critical activities.

## Slide 25: Solution Step-1: Calculate ES and EF

## Slide 26: Step-2: Calculate LS and LF

## Slide 27: Step-3: Calculate Total float

## Slide 28: Step 4: Indicate critical activities

## Slide 29: Problem-3
Given below the precedence network for a small engineering project with activity durations in working days. Compute the activity times (ES, EF, LS, and LF), total floats (TF) and free floats. Also indicate the critical activities and find the critical path.
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | LEGENDS |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ES | D | EF
 |  |  |  |  |  | 3 |  | SF,2 |  |  | 2 |  |  |  |  |  |  |  |  |  |  | Act | FF
 |  |  |  |  |  | B |  |  |  |  | D |  |  |  |  |  |  |  |  |  | LS | TF | LF
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 3 |  |  |  |  | 
 |  |  |  | SS, 2 |  |  |  |  |  |  |  |  |  |  |  |  |  | F |  |  |  |  | 
 | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | FF,1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 6 |  |  |  |  | 6 |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | C |  | FS,1 |  |  | E |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 30: Solution Step-1: ES and EF Calculations

## Slide 31: Step-2: LF and LS Calculations

## Slide 32: Contd.
 |  |  |  |  | 2 | 3 | 5 | SF,2 |  | 2 | 2 | 4 |  |  |  |  |  |  | 
 |  |  |  |  |  | B |  |  |  |  | D |  |  |  |  |  |  |  | 
 |  |  |  |  | 11 | 9 | 14 |  |  | 11 | 9 | 13 |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 13 | 3 | 16
 |  |  |  | SS, 2 |  |  |  |  |  |  |  |  |  |  |  |  |  | F | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 13 | 0 | 16
0 | 5 | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
0 | 0 | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | FF,1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | 0 | 6 | 6 |  |  | 7 | 6 | 13 |  |  |  |  |  |  | 
 |  |  |  |  |  | C |  | FS,1 |  |  | E |  |  |  |  |  |  |  | 
 |  |  |  |  | 0 | 0 | 6 |  |  | 7 | 0 | 13 |  |  |  |  |  |  | 

## Slide 33: Step-3: FF Calculations

## Slide 34: Final Answer
 |  |  |  |  | 2 | 3 | 5 | SF,2 |  | 2 | 2 | 4 |  |  |  |  |  |  | 
 |  |  |  |  |  | B | 0 |  |  |  | D | 9 |  |  |  |  |  |  | 
 |  |  |  |  | 11 | 9 | 14 |  |  | 11 | 9 | 13 |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 13 | 3 | 16
 |  |  |  | SS, 2 |  |  |  |  |  |  |  |  |  |  |  |  |  | F | 0
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 13 | 0 | 16
0 | 5 | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | A | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
0 | 0 | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | FF,1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | 0 | 6 | 6 |  |  | 7 | 6 | 13 |  |  |  |  |  |  | 
 |  |  |  |  |  | C | 0 | FS,1 |  |  | E | 0 |  |  |  |  |  |  | 
 |  |  |  |  | 0 | 0 | 6 |  |  | 7 | 0 | 13 |  |  |  |  |  |  | 
Critical Activities: A; C; E; and F
Critical Path: A-C-E-F

## Slide 35: Hammock Activity
An activity that extends from one activity to another, but which has no estimated duration of its own.
It is time-consuming and requires resources, but its duration is controlled, not by its own nature, but by the two activities between which it spans.
  Example: activity “A” ends on day 3 and activity “C” begins on day 10 and there is a set of activities that are summarized as activity “B” (the hammock activity) that must be done between activity “A” and activity “C.”
  Activity “B” doesn’t have a specific duration—it has the duration of the time between day 3 and day 10.
  If activity “A” takes longer than expected and ends on day 4, then the duration of activity “B” is now the duration of time between day 4 and day 10.
Its ES and LS times are determined by the activity where it begins and its EF and LF times are dictated by the activity at its conclusion.
Notes: a type of bed made from a net or from a piece of strong material, with ropes at each end that are used to hang it between two trees, posts, etc.

## Slide 36: Milestones
Milestones are points in time that have been identified as being important intermediate reference points during the accomplishment of the work
Milestone events can include dates imposed by the customer for the finishing of certain tasks as well as target dates set by the project manager for the completion of certain segments of the work.
Distinctive geometric figure is preferred to represent a milestone (circles, ovals, or other shapes can be used).

## Slide 37: Shortening of Project Duration
Reducing scope (or quality)
Adding resources
Concurrency (perform tasks in parallel)
Substitution of activities

## Slide 38: Further Reading
Moder J., Phillips, C., and Davis, E. Project Management with CPM, PERT, and Precedence Diagramming, 3rd Edition.
Jimmie W. Hinze. “Construction Planning and Management,” Fourth Edition, 2012, Pearson.
Read more about the scheduling network models from:

## Slide 39: Thank You
Questions Please