## Slide 1: Time Planning and Control Precedence Diagram

## Slide 2
Precedence Diagramming
An important extension to the original activity-on-node concept appeared around 1964.
The sole relationship used in PERT/CPM network is finish to start type of dependency, with Fsij = 0 .
Precedence diagramming includes precedence relationships among the activities. In Addition, one may specify a “lag time” associated with any of the precedence relationships, which can be used to account for overlapping times among activities.
The computation of activity times (published in 1973) is more complex than AON.
EF | D |  | ES
Activity ID |  |  | 
LF | TF | LS | 

## Slide 3
In many cases, there is a delay between the completion of one activity and the start of another following or there is a need to show that one activity will overlap another in some fashion.
A successor "lags" a predecessor, but a predecessor "leads" a successor.
Lag time can be designated on a dependency line with a positive, negative, or zero value.
Limitations and Disadvantages of Lag:
  Lag would complicate the scheduling process.
  Lags are not extensively used except where the time effects are substantial for special project type.
Lag / Lead Times
EF | D |  | ES
Activity ID |  |  | 
LF | TF | LS | 

## Slide 4
Precedence Diagramming Relationships Types and constraint
  Start-to-Start (SSij)
  [(j) cannot start till (i) starts by amount of the SS]
The value of SSij is equal to the minimum number of time units that must be completed on the preceding activity (i) prior to the start of the successor (j). “Lag” is always applied to SS relation.
Example SSij =3 [The start of (j) must lag 3 units after the start of (i)]
 | i | 
SSIJ | j | 
  Finish-to-Finish (FFij)
  [(j) cannot finish till (i) finishes by amount of the FF]
FFij is equal to the minimum number of time units that must remain to be completed on the successor (j) after the completion of the predecessor (i).
Example FFij =5 [The finish of (j) must lag 5 units after the finish of (i) ]
i |  | FFIJ
 | j | 

## Slide 5
Precedence Diagramming Relationships Types and constraint
Finish-to-Start (FSij)
[(j) cannot start till (i) finishes by amount of the FS]
FSij is equal to the minimum number of time units that must transpire from the completion of the predecessor (i) prior to the start of the successor (j).
Example FSij =6 [The start of (j) must lag 6 units after the finish of (i)]
i | FSIJ | j
Start-to-Finish (SFij)
  [(j) cannot finish till (i) starts (rare)]
SFij is equal to the minimum number of time units that must transpire from the start of the predecessor (i) to the completion of the successor (j).
Example SFij (SFij ‘ + SFij “) =(4+6) =10 [The finish of (j) must lag 10 units after the start of (i)]
SFij' |  |  | 
 |  | i | 
 | j |  | 
 |  | SFij'' | 

## Slide 6
Precedence Diagramming Relationships Types and constraint
Start-to-Start and Finish-to-Finish (ZZij):
ZZij is a combination of two constraints, i.e., a start-to-start and finish-to-finish relationship. It is written with the SSij time units first, followed by the FFij time units.
Example ZZij =5 , 6 [The start of (j) must lag 5 units after the start of (i) (SSij = 5) & The finish of (j) must lag 6 units after the finish of (i) (FFij = 6)]
ES | Duration | EF
Activity (i) |  | 
LS | Total Float | LF
ES | Duration | EF
Activity (j) |  | 
LS | Total Float | LF
Types of constraints with lag/lead Durations

## Slide 7
Precedence Diagram Computation
Forward Pass Computations |  |  | 
[1] ESj = | Max. all i |  | Initial Time EFi + FSij ESi + SSij EFi + FFij – Dj ESi + SFij - Dj
[2] EFj = ESj + Dj |  |  | 
EF | D |  | ES
FF | Activity ID |  | 
LF | TF | LS | 

## Slide 8
Precedence Diagram Computation
Backward Pass Computations |  |  | 
[3] LFi = | Min. all j |  | Terminal Time LSj - FSij LFj - FFij LSj - SSij + Di LFj - SFij + Di
[4] LSi = LFi  Di |  |  | 
EF | D |  | ES
FF | Activity ID |  | 
LF | TF | LS | 

## Slide 9
Precedence Diagramming Calculations
EXAMPLE
For the given precedence diagram, complete the forward and backward pass calculations. Assume the project starts at T=0, and no splitting on activities is allowed. Also assume that the project latest allowable completion time (project duration) is scheduled for 30 working days.
FS 0
SS 3
FF 4
SS 6
SF 12
FS 0
A
Develop system spec.
(D=8)
C
Collect system data
(D=4)
D
Test & debug program
(D=6)
E
Run program
(D=6)
F
Decument program
(D=12)
B
Write comp. program
(D=12)

## Slide 10
Precedence Diagramming Calculations
AON diagram
A
8
B
12
D
6
C
4
END
0
E
6
F
12
FS 0
SS 3
FF 4
SS 6
SF 12
FS 0
A
Develop system spec.
(D=8)
C
Collect system data
(D=4)
D
Test & debug program
(D=6)
E
Run program
(D=6)
F
Decument program
(D=12)
B
Write comp. program
(D=12)

## Slide 11
Precedence Diagramming Calculations
Example Computation
Forward Pass Computations
Activity A
Activity B
Activity C
A
8
B
12
D
6
C
4
END
0
E
6
F
12
0
8
3
15
9
13
FS 0
SS 3
FF 4
SS 6
SF 12
FS 0

## Slide 12
Precedence Diagramming Calculations
Example Computation
Forward Pass Computations
A
8
B
12
D
6
C
4
END
0
E
6
F
12
0
8
3
15
9
13
Activity D
Activity E
Activity F
15
21
21
27
15
27
27
27
FS 0
SS 3
FF 4
SS 6
SF 12
FS 0

## Slide 13
Precedence Diagramming Calculations
Example Computation
A
8
B
12
D
6
C
4
END
0
E
6
F
12
0
8
3
15
9
13
15
21
21
27
15
27
27
27
Activity F
Activity E
Activity D
Backward Pass Computations
30
30
3
30
30
18
3
24
3
24
18
3
FS 0
SS 3
FF 4
SS 6
SF 12
FS 0

## Slide 14
Precedence Diagramming Calculations
Example Computation
Backward Pass Computations
A
8
B
12
D
6
C
4
END
0
E
6
F
12
0
8
3
15
9
13
15
21
21
27
15
27
27
27
30
30
3
30
30
18
3
24
3
24
18
3
18
14
5
18
6
3
11
3
3
Activity C
Activity B
Activity A
FS 0
SS 3
FF 4
SS 6
SF 12
FS 0

## Slide 15
Precedence Diagramming Calculations
Earliest Earliest Latest Latest On Start Finish Start Finish Slack Critical Activity ES EF LS LF LS – ES Path
A 0 8 3 11 3 No
B 3 15 6 18 3 No
C 9 13 14 18 5 No
D 15 21 15 21 3 No
E 21 27 24 30 3 No
F 15 27 18 30 3 No
Computing Slack Time (Float Time)

## Slide 16
Given the precedence network for a small engineering project with activity durations in working days, it is required to compute the activity times (ES, EF, LS, and LF) and total floats (TF) and then indicate the critical activities.
Example 2
EF | D |  | ES
FF | Activity ID |  | 
LF | TF | LS | 

## Slide 17: Example 2
Calculate the Early activity times (ES and EF).
EF | D |  | ES
FF | Activity ID |  | 
LF | TF | LS | 

## Slide 18: Example 2
Calculate the late activity times (LS and LF).
EF | D |  | ES
FF | Activity ID |  | 
LF | TF | LS | 

## Slide 19: Example 2
Calculate Total Float for an activity.
EF | D |  | ES
FF | Activity ID |  | 
LF | TF | LS | 

## Slide 20
Example 2
Indicate the critical activities.
EF | D |  | ES
FF | Activity ID |  | 
LF | TF | LS | 

## Slide 21
An activity that extends from one activity to another, but which has no estimated duration of its own.
It is time-consuming and requires resources, but its duration is controlled, not by its own nature, but by the two activities between which it spans.
Its ES and LS times are determined by the activity where it begins and its EF and LF times are dictated by the activity at its conclusion.
Examples: Dewatering, Haul road maintenance
HAMMOCK ACTIVITY
Notes on Schedule

## Slide 22
Milestones are points in time that have been identified as being important intermediate reference points during the accomplishment of the work.
Milestone events can include dates imposed by the customer for the finishing of certain tasks as well as target dates set by the project manager for the completion of certain segments of the work.
MILESTONES
Notes on Schedule

## Slide 23
Distinctive geometric figure is preferred to represent a milestone (circles, ovals, or other shapes) can be used.
Any information pertaining to a milestone and considered to be useful may be entered.
MILESTONES
Notes on Schedule

## Slide 24
How can you shorten the schedule?
Via
  Reducing scope (or quality)
  Adding resources
  Concurrency (perform tasks in parallel)
  Substitution of activities
Reducing Project Duration
Notes on Schedule